## Slide 1
PART 5 · SUMMARY
€120k signs 100 maintenance hires by 31 Dec, if the client assesses 55 a week
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
€120k
budget: €100k plan + €20k reserve
€1,000
cost per hire (€1,200 all-in)
98%
of 314 assessment slots used
Role | Hires | Spend | € / hire
Electricians | 30 | €38.7k | €1,291
Mechatronics | 45 | €29.9k | €664
Automation | 15 | €16.6k | €1,106
Supervisors | 10 | €14.8k | €1,476
Total | 100 | €100k | €1,000
Top 3 risks → action
Capacity: pace ≤55 assessments a week; ask for +9 slots.
Electricians: construction-electrician route needs the client's OK by 23 Oct.
Christmas: offers within 3 days; last applications Tue 24 Nov.
What I need from you
• 55 assessments a week from 22 Oct
• Day-1 export of past applicants
• €1,000 referral bonus
• Construction-electrician decision by 23 Oct
• Approve €120k

## Slide 2
PART 1 · FUNNEL
100 hires need ~311 qualified applicants; the plan brings 308 for 314 slots
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Role | Hires | App → qualified | Qualified → passed | Passed → offer | Offer → signed | Qualified needed | Applications needed
Electricians | 30 | 25% | 50% | 90% | 70% | 95 | 381
Mechatronics | 45 | 25% | 55% | 90% | 75% | 121 | 485
Automation | 15 | 25% | 45% | 90% | 70% | 53 | 212
Supervisors | 10 | 23% | 40% | 85% | 70% | 42 | 183
Total | 100 |  |  |  |  | 311 | 1,260
Sources: IAB (1 in 4 applications suitable), Gem (pass rates), Königsteiner (offer acceptance). All labelled on the Inputs tab.
Capacity: assessments run 22 Oct – 30 Nov (40 days): 55 × 40 ÷ 7 = 314 slots. The plan uses 98%.
Last useful application: 18 Dec signature − 7 − 3 − 8 − 6 days = Tue 24 Nov (supervisors Tue 17 Nov).

## Slide 3
PART 1 · HARDEST ROLE AND MOST SENSITIVE ASSUMPTION
Electricians are hardest; a 30% worse pass rate leaves ~71 hires
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Why electricians
• Scarcest trade in Brandenburg: 85.7% of vacancies have no suitable jobseeker, vs 41.4% overall (KOFA 2026).
• Dearest cost per hire: €1,291.
• No Polish route, and foreign-trained electricians need 2–4 months of recognition.
Most sensitive: the pass rate
• 30% worse pass rate → 440 qualified needed for 314 slots → ~71 hires.
• Money can't fix it: the slots are full.
• A lower share qualified or dearer clicks only cost money, not hires.
• First read on 2 Nov; if low, tighten screening questions and ask for more slots.

## Slide 4
PART 2 · CHANNELS
Each role buys its hires from the cheapest source first
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Source | Roles | Spend | € / hire | Hires
Organic | E M A S | €0 | €0 | 20.0
Past applicants | E M A S | €65 | €14 | 4.7
Polish border corridor | M | €6.9k | €383 | 18.0
Employee referrals | E M A S | €11k | €1,000 | 11.0
Construction electricians | E | €11.1k | €1,329 | 8.4
StepStone | E M | €5.8k | €1,567 | 3.7
LinkedIn | A S | €28.6k | €1,688 | 16.9
Programmatic | E M | €36.5k | €2,116 | 17.3
Total |  | €100k | €1,000 | 100
How it works
• Cost per hire = cost per application ÷ share qualified ÷ qualified → signed.
• Each source is capped by how many people it can reach.
• Every paid source starts with a €750 test in weeks 1–2.
• E electricians · M mechatronics · A automation · S supervisors.

## Slide 5
PART 2 · BUDGET
€100k planned, paced to the assessment slots, plus a €20k reserve
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Week | Spend | Qualified arriving | Slots
Wk 1 | €27.5k | 85 | 86
Wk 2 | €17.5k | 54 | 55
Wk 3 | €17.5k | 54 | 55
Wk 4 | €17.5k | 54 | 55
Wk 5 | €17.5k | 54 | 55
Wk 6 | €2.5k | 8 | 8
Total | €100k | 308 | 314
Testing: €6k in weeks 1–2 (€750 per paid source and role).
Money moves: weak sources cut from Mon 2 Nov; strong ones get +25% a week.
Reserve: €20k (15% + rounding), released only on results.
Spend stops: Tue 24 Nov, the last useful application date.
Why week 1 is biggest: its applicants fill 11 days of assessments (22 Oct – 1 Nov).

## Slide 6
PART 2 · SMALLER BUDGET
30% less (€84k) signs ~87; electricians and supervisors fall short first
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Role | Recommended | 30% less
Electricians | 30 | 20.6
Mechatronics | 45 | 45.0
Automation | 15 | 15.0
Supervisors | 10 | 6.3
Total | 100 | 86.9
Rule: cut the dearest cost-per-hire sources first; keep the 15% reserve.
Falls short: electricians (programmatic is their dearest source) and supervisors (LinkedIn).
What I'd tell the client: the last €36k buys ~13 hires, mostly electricians. Keep it; if you must cut, cover supervisors by internal promotion.

## Slide 7
PART 3 · NEW SOURCES
Three new sources supply ~42 of the 100 hires, one built for electricians
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Past applicants + referrals
• Who: ~211 past runners-up (estimate) + staff referrals
• How: email/SMS on days 2, 7, 14; €1,000 per signed referral
• Maths: ~16 hires for ~€11k
• Test 21 Oct – 3 Nov: pass ≥14 qualified, kill <8
• Setup 1 day. Client: GDPR-checked export
Construction electricians
• Who: ~10,000 within 75 km (BA)
• How: social ads + 6-question quiz; 2–4 week bridge course
• Maths: 118 apps × €84 + €1.2k → 8.4 hires (€1,329 each)
• Test 23 Oct – 5 Nov: pass ≥7 qualified at ≤€500
• Setup 3 days. Client: profile OK by 23 Oct
Polish border corridor
• Who: mechatronics workers 60–130 km away (EU)
• How: Polish job boards + a Polish-speaking pre-screener
• Maths: 346 apps × €18.75 + €400 → 18 hires (40% cap)
• Test 27 Oct – 9 Nov: pass ≥12 qualified at ≤€200
• Setup 1 week. Client: approve the ads
Repeatable Joveo product: past-applicant rediscovery — every employer holds consented past applicants; Joveo can add them as one more tracked source in any market.

## Slide 8
PART 4 · RUN IT WEEK BY WEEK
Track by source and role, move money on simple rules, check the riskiest assumptions early
Operation Uptime · all figures from Operation_Uptime_Simple_Model.xlsx
Track every Monday
• Spend, applications, qualified by source × role
• Assessed, passed, offers, signed by role (ATS source tag)
• Data: Joveo tracked links + Monday ATS export
Money rules
• Judge after €500 or 30 applications
• 20% cheaper than plan → +25% a week; 50% dearer → halve; 2× → off
• Over 55 qualified next week → pause the dearest
Week-2 checks
• Pass rate (read 2 Nov): if low → sharper screening, more slots
• Construction-electrician quality (9 Nov): if poor → programmatic fills the gap
• Real test costs: re-rank sources
First five actions
• Tue 20 Oct: kick-off; lock slots, dates, bonus
• Tue–Wed: launch sources and tests
• Wed 21 Oct: past-applicant wave + referrals
• Fri 23 Oct: construction campaign live
• Mon 26 Oct: first read-out