## Slide 1: €122.5k signs 100 maintenance hires by 31 Dec, if the client can assess 55 a week
PART 5 · SUMMARY FOR THE HEAD OF TALENT ACQUISITION
€122.5k
budget: €102.3k plan + €20.2k reserve, released only on results
€1,023
media cost per hire (€1,225 if the reserve is spent)
98%
of 314 assessment slots used: capacity, not money, is the limit
Plan
€750 test in each pay-per-click channel in weeks 1–2, then buy hires cheapest first.
Three new sources bring ~42 hires: past applicants + referrals, construction electricians, Polish border towns.
Pace ≤55 assessments a week; applications until Tue 24 Nov, signatures by Fri 18 Dec.
How sure: 100 if funnel rates hold, with no slack (98% of slots used); pass rate 10% worse → ~92; 30% less budget → ~87.
Role | Hires | Spend | € / hire
Electricians | 30 | €39.1k | €1,304
Mechatronics | 45 | €30.1k | €670
Automation | 15 | €17.4k | €1,162
Supervisors | 10 | €15.5k | €1,555
Total | 100 | €102.3k | €1,023
Top 3 risks → what I'll do
Assessment capacity: pace ≤55 a week, pre-screened sources first, ask for +9 slots. If assessments can't start 22 Oct: ~92 hires (100 then needs 60 a week).
Electrician supply: construction-electrician route needs your OK by 23 Oct; without it €130k.
Christmas: offers within 3 days, e-signature, stop spend Tue 24 Nov. At German process pace (8 + 12 days): ~92 hires; +9 slots a week restores 100.
What I need from you
55 assessments a week from Thu 22 Oct (+9 if possible)
Day-1 export of past applicants (GDPR-checked)
€1,000 referral bonus + one staff message
Construction-electrician decision + bridge-course trainer by 23 Oct
Approve €122.5k
Notes: Part 5 one-page summary. All figures come from the model's Summary, Budget and Funnel tabs.

## Slide 2: Working back from 100 hires: ~308 qualified applicants for 314 assessment slots
PART 1 · BUILD THE FUNNEL
Role | Hires | App → qualified | Qualified → passed | Passed → offer | Offer → signed | Qualified needed | Applications needed
Electricians | 30 | 25% | 50% | 90% | 70% | 95 | 381
Mechatronics | 45 | 25% | 55% | 90% | 75% | 121 | 485
Automation | 15 | 25% | 45% | 90% | 70% | 53 | 212
Supervisors | 10 | 23% | 40% | 85% | 70% | 42 | 183
Total | 100 |  |  |  |  | 311 | 1,260
Where the rates come from: IAB (about 1 in 4 applications is suitable), Gem (interview pass rates), German offer-acceptance surveys. Each one is labelled on the Assumptions tab.
Latest useful application: work back from the last signature, Fri 18 Dec: offer → signed 7 days, interview → offer 3, assessment → interview 8, application → assessment 6. So applications must arrive by Tue 24 Nov (supervisors Tue 17 Nov).
Capacity check
98%
308 qualified applicants in the plan (from 1,495 applications) against 314 slots: 55 a week × 40 assessment days ÷ 7.
The plan fits, but with almost no headroom. Every week is paced to stay within 55 (Weekly tab).
Why 308, not 311: referrals and past applicants convert better than the table's standard rates, so the plan needs slightly fewer. Applications: 1,495, not 1,260, because the plan's channels average 21% qualified (social ads lower), below the ~25% baseline.

## Slide 3: Electricians are hardest; a 30% worse pass rate costs ~29 hires that money can't buy back
PART 1 · HARDEST ROLE AND MOST SENSITIVE ASSUMPTION
Why electricians are hardest
Scarcest trade in Brandenburg: 85.7% of vacancies have no suitable unemployed candidate, against 41.4% across all jobs (KOFA 2026).
Dearest last hire: €2,272, the highest of the four roles (Funnel column H).
No back door: no Polish route, and foreign-trained electricians need 2–4 months of recognition.
Automation has a tighter pool and less channel headroom (22% of reachable people vs 12%), but needs only 15 and costs less per hire, so it is watched weekly.
Chart: Hires possible by 31 Dec if one input is 30% worse
| Base case | Pass rate ×0.7 | Acceptance ×0.7 | Share qualified ×0.7 | Cost per app ×1.3 | Capacity ×0.7 (given)
Hires possible by 31 Dec | 100 | 71 | 71 | 100 | 100 | 71
Most sensitive: the pass rate. 30% worse means 440 qualified applicants for 314 slots, so only ~71 can be hired; spending more doesn't help. Acceptance ties, but fast offers protect it; the pass rate depends on the plant's own test and is only known after interviews (week-2 check). A weaker share qualified or dearer clicks only cost money, not hires: a 30% lower share qualified needs a €185k budget on a full re-run (cheap channels hit their caps); dearer clicks +30% media.

## Slide 4: Every role buys its hires cheapest cost-per-hire first
PART 2 · CHANNELS, RANKED BY COST PER HIRE
Channel | Roles | Why | Spend | € / qualified | € / hire | Hires
Organic | E M A S | Free: careers site, BA Jobbörse, Google for Jobs | €0 | €0 | €0 | 20.0
Rediscovery | E M A S | Past applicants, already screened | €63 | €5 | €14 | 4.6
Polish corridor | M | Large pool across the border (≤40% of mechatronics) | €6.9k | €142 | €383 | 18.0
Referrals | E M A S | Staff know the job; €1,000 bonus on signing | €11k | €370 | €1,000 | 11.0
Handwerk→Industrie | E | Construction electricians: a new pool for the hardest role | €11.1k | €377 | €1,329 | 8.4
StepStone | E M | Germany's main CV job board | €5.8k | €537 | €1,564 | 3.7
LinkedIn | A S | PLC and Meister profiles (automation, supervisors) | €27.2k | €444 | €1,687 | 16.1
Programmatic | E M A S | Indeed and other boards, paid per application | €35.7k | €717 | €2,142 | 16.7
Meta | E M | Reaches people who aren't job-hunting | €1.5k | €820 | €2,388 | 0.6
Google Search | E M A S | High intent, but the dearest | €3k | €1,044 | €3,442 | 0.9
Total |  |  | €102.3k |  | €1,023 | 100
How it works
Cost per hire = cost per application ÷ share qualified ÷ qualified → signed.
Each channel is capped by how many people in the local talent pool it can reach.
Each pay-per-click channel gets a €750 test per role first; Search and Meta stay at test level, and so does programmatic for automation and supervisors.
Roles: E electricians, M mechatronics, A automation, S supervisors.
Per channel × role: Channels tab (cost per qualified col O, per hire col P, rank col AC).

## Slide 5: €102.3k planned across roles and weeks, plus a €20.2k reserve
PART 2 · BUDGET, ALLOCATION AND PHASING
Chart: Cash out by week (€)
| Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9
Tests (€750 per channel) | 3600 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paid media | 21494 | 10800 | 13258 | 13992 | 13524 | 1814 | 0 | 0 | 0
StepStone ads + set-up | 7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Referral bonuses | 0 | 0 | 0 | 3119 | 1728 | 1769 | 1899 | 2158 | 305
Role | Spend | Hires | € / hire
Electricians | €39.1k | 30 | €1,304
Mechatronics | €30.1k | 45 | €670
Automation | €17.4k | 15 | €1,162
Supervisors | €15.5k | 10 | €1,555
Total | €102.3k | 100 | €1,023
Testing: €9k in weeks 1–2: 12 tests of €750 (programmatic, LinkedIn, Meta, Search × role).
Moving money: weak channels cut from Mon 2 Nov; tests judged by Mon 9 Nov.
Reserve: €20.2k (15% + rounding), released from week 3 only on results.
Paid media stops: Tue 24 Nov, the last useful application date (referral bonuses are paid as people sign).
Why week 1 is biggest: assessments start 22 Oct and an unused slot is lost, so week-1 applications must fill 11 days of slots (22 Oct – 1 Nov). The tests then decide where weeks 3–6 money goes. Week 6 is small: only 24 Nov is still a useful application day.

## Slide 6: 30% less (€85.75k) signs ~87; electricians fall short first
PART 2 · WHAT A SMALLER BUDGET BUYS
Chart: Hires by role
| Electricians | Mechatronics | Automation | Supervisors
Recommended (€122.5k) | 30 | 45 | 15 | 10
30% less (€85.75k) | 20.5 | 44 | 14.5 | 8.1
Budget | Hires | € per hire (all-in)
Recommended · €122.5k | 100 | €1,225
30% less · €85.75k | 87 | €985
Rule: cut the most expensive cost-per-hire channels first; keep the reserve at 15%.
Falls short first: electricians 20.5 of 30, supervisors 8.1 of 10, mechatronics 44.0 of 45, automation 14.5 of 15.
What I'd tell the client: the last €36.75k buys ~13 hires, mostly electricians, the people who keep the lines running. Keep it. If you must cut, the rule cuts the dearest channels, which are mostly electrician and supervisor channels: agree that up front, and cover supervisors by internal promotion.

## Slide 7: Three new sources supply ~42 of the 100 hires, one built for electricians
PART 3 · NEW SOURCES BEYOND THE USUAL PAID CHANNELS
I1 · ATS rediscovery + referral sprint
Who: ~211 past runners-up from the last 12 months (my estimate; the real export replaces it on day 1) + staff referrals
How: Email + SMS waves on days 2, 7 and 14; €1,000 bonus per signed referral
Why better: Already screened and already wanted Tesla; ~€2.50 per application
Maths: €63 + €11k bonuses → 25 re-apps + 66 referrals → ~42 qualified → ~16 hires
2-week test: Wed 21 Oct – Tue 3 Nov (waves 1–3): €63. Pass: ≥14 qualified. Kill: <8 → no further re-contacts; bonus stays live
Who does what: Setup 1 day (live Wed 21 Oct). Me: copy, segments, tracked links. Client: GDPR-checked export, bonus approval, one staff message
I2 · Handwerk → Industrie (electricians)
Who: ~10,000 construction electricians within 75 km
How: Social and search ads with a 6-question quiz; Tesla runs a 2–4 week bridge course
Why better: Certified electricians who never search for plant jobs; more than doubles the hardest pool (10,000 vs 4,800)
Maths: 118 apps × €84 = €9.9k + €1.2k set-up → 30 qualified × 28% = 8.4 hires (€1,329/hire)
2-week test: Fri 23 Oct – Thu 5 Nov (read Mon 9 Nov): €5.6k. Pass: ≥7 qualified at ≤€500. Kill: <4, >€670 per qualified, or profile rejected
Who does what: Setup 3 days (live Fri 23 Oct). Me: ads, quiz, German copywriter. Client: profile sign-off by 23 Oct; its maintenance trainers run the 2–4 week bridge course after signing (onboarding time, not campaign budget)
I3 · Polish border corridor + pre-screener
Who: Mechatronics workers in Polish border towns, 60–130 km away (EU)
How: Polish job boards and Meta; a Polish-speaking freelancer phones each applicant (15 min)
Why better: ~1,700 Polish machine, metal and building workers already commute to Brandenburg (IAB 2020); the call checks language before using our slots. If response is only I2's rate (~219 applications): €132.5k; if it fails: €155k
Maths: 346 apps × €18.75 + €400 → 48 qualified × 37% = 18.0 hires (40% of mech, cap 40%)
2-week test: Tue 27 Oct – Mon 9 Nov (freelancer starts 27 Oct): €3.2k. Pass: ≥12 qualified at ≤€200. Kill: <7, >€270 per qualified, or too few pass the language call
Who does what: Setup 1 week (live Tue 27 Oct). Me: Polish ads, hire the freelancer via rocketjobs.pl (~€19/h), call script, weekly call checks. Client: approve the ads
Repeatable Joveo product: ATS rediscovery. Employers that keep consented past applicants rarely run campaigns to them. Here ~211 records (my estimate) cost ~€14 per hire and fill week-1 slots. Joveo already runs the tracked links and distribution, and its Talent CRM re-engages past applicants, so a consented past-applicant feed becomes one more tracked source, in any market, with no local staff.

## Slide 8: Track by source × role weekly, move money on rules, test the riskiest assumptions early
PART 4 · RUN IT WEEK BY WEEK
Track (every Monday)
By source × role: spend, applications, qualified. By role: assessed, passed, offers, signed (each hire keeps its ATS source tag)
Data: Joveo tracked links + Monday ATS export (source tag), recruiter codes, pre-screener sheet
Tracker tab turns this into decisions and a hire forecast
Money rules
Judge a channel only after €500 or 30 applications
20% cheaper than plan → +25% a week from the reserve; 50% dearer → halve; 2× → off
Over 55 qualified next week → pause the dearest; under 50 → release reserve
Check by Mon 2 Nov (confirm 9 Nov)
Pass rate: first read 2 Nov, confirmed 9 Nov once a role has 10 interviews; if low → tighter knock-out questions, ask for more slots (10% lower ≈ 92 hires)
Construction electricians: if stopped, programmatic fills the gap (€130k)
Real test costs: re-rank channels; acceptance read after 5 offers
First five things in week 1
Tue 20 Oct: kick-off with client; lock slots, 18 Dec date, bonus; request ATS export
Tue–Wed: launch channels and tests with tracked links
Wed 21 Oct: past-applicant wave 1 + referral launch
Wed–Fri: set up Polish ads + freelancer (live 27 Oct); construction campaign live 23 Oct
Mon 26 Oct: first read-out