## Summary
Operation Uptime — model summary (hypothetical Tesla Giga Berlin maintenance hiring)
Everything on this tab is a live link to the model. Inputs live only on the Assumptions tab (blue on yellow).
Target: signed contracts by 31 Dec | 100
Recommended budget | 122500
…of which planned spend | 102255.8476
…of which reserve (incl. rounding up) | 20244.1524
Hires the channel plan buys | 100
Hires actually possible (≤ 55 assessments/week) | 100
Media cost per hire | 1022.5585
Qualified applicants to assess | 307.9731
Assessment slots available (capacity × weeks) | 314.2857
Slot utilisation | 97.99%
Last useful application date (E/M/A) | 2026-11-24
Last useful application date (Supervisors) | 2026-11-17
Hardest role (dearest last hire we must buy; reasons on Funnel row 35) | Electricians (last hire costs €2,272)
Most sensitive assumption | Qualified → signed (assessment pass rate) ×0.7
Hires with 30% less budget | 87.0578
Input checks | ✓ all inputs valid
Plan / schedule check (Weekly S15) | ✓ ties to plan
Tabs: Assumptions (every input, its label and source link) → Funnel (Part 1, with the talent-pool check) → Channels (Part 2.2–2.3) → Initiatives (Part 3) → Budget (Part 2.4–2.5, with the budget-cut scenarios) → Weekly (phasing and cash) → Tracker (Part 4, live re-plan).

## Assumptions
Assumptions log = the model's only input sheet
Blue cells on yellow are inputs: change them here and every other tab recalculates. Labels: Given = from the brief; Researched = read from, or calculated by stated arithmetic from, the linked source; Own estimate = my judgement, with the reason (and the benchmark it starts from, where there is one). Black (not blue) values are calculated.
1. Given in the brief
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
G1 | Campaign start | All | 2026-10-20 | date | Given | From the brief.
G2 | Campaign end / hire deadline (signed contract) | All | 2026-12-31 | date | Given | From the brief.
G3 | Recruiter capacity: qualified applicants assessed per week | All roles | 55 | per week | Given | From the brief.
G4 | Max share of mechatronics/mechanical hires from Polish sources | Mechatronics | 40% | % | Given | From the brief. Polish hires need no work permit (EU free movement) and are insured and taxed in Germany. https://www.make-it-in-germany.com/en/working-in-germany/information-eu-citizens/print
G5 | Openings | Electricians | 30 | hires | Given | From the brief.
G6 | Openings | Mechatronics | 45 | hires | Given | From the brief.
G7 | Openings | Automation | 15 | hires | Given | From the brief.
G8 | Openings | Supervisors | 10 | hires | Given | From the brief.
G9 | Foreign electrical qualification recognition time (info only: makes foreign-trained electricians unhireable by 31 Dec) | Electricians | 2 | months (min) | Given | From the brief, so I plan no foreign-trained electricians. Worth raising: for employees the trade is not legally regulated, which could open this route. https://www.anerkennung-in-deutschland.de/en/interest/finder/profession/62/profile
2. Hiring timeline (sets the last useful application date)
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
T0 | Days from campaign start to first assessments | All | 2 | days | Own estimate | Own estimate, not sourced: at launch there is no queue, so the first applicants and re-applicants are assessed within 2 days (SmartRecruiters' 6-day median review, T2, applies once a queue exists and sets the cut-off). If first assessments slip to 26 Oct, hires fall to ~92 (model run); 100 would then need 60 a week.
T1 | Last realistic contract-signing date | All | 2026-12-18 | date | Own estimate | My choice: the last Friday before Christmas. Indeed job searches fall to 45% below the 1–15 Dec average over the holidays (Indeed Hiring Lab). https://hiringlab.indeed.com/de/blog/2025/02/17/der-stellenmarkt-startet-unausgewogen-in-das-neue-jahr/
T2 | Days: application → recruiter assessment of a qualified applicant | All | 6 | days | Researched | Own estimate: SmartRecruiters 2025 global median is 6 days to review (Germany 8); I assume the client keeps the global pace, an ask. Slide 1 shows the German-pace downside (~92 hires). https://ta.smartrecruiters.com/rs/664-NIC-529/images/Germany%20Recruiting%20Benchmarks%202025%20Report%20DE.pdf
T3 | Days: recruiter assessment → technical interview/test done | All | 8 | days | Own estimate | Own estimate: global median 14 days application → interview minus the 6 above (Germany 20 − 8 = 12); same commitment as T2. https://ta.smartrecruiters.com/rs/664-NIC-529/images/Germany%20Recruiting%20Benchmarks%202025%20Report%20DE.pdf
T4 | Days: interview → written offer | All | 3 | days | Own estimate | My ask to the client: written offer within 3 working days. No public benchmark exists for this step.
T5 | Days: offer → signed contract | All | 7 | days | Own estimate | One-week offer validity; candidates take ~9 days on average to decide (NACE 2025). https://www.naceweb.org/talent-acquisition/trends-and-predictions/employers-make-more-offers-as-student-acceptance-rate-rises-response-time-shortens
T6 | Extra days for supervisors (second round with plant management) | Supervisors | 7 | days | Own estimate | Supervisors have one extra round with plant management (about a week).
3. Funnel rates by role (Part 1)
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
QE | Application → qualified (baseline, all channels) | Electricians | 25% | % | Researched | IAB 2026 chart: production jobs get 12 applications per vacancy, 3 suitable (25%); 28% across all jobs; 23% for specialist roles. https://iab-forum.de/iab-stellenerhebung-2-2026-fast-drei-von-vier-bewerbungen-sind-aus-betrieblicher-sicht-ungeeignet/
QM | Application → qualified (baseline, all channels) | Mechatronics | 25% | % | Researched | IAB 2026 chart: production jobs get 12 applications per vacancy, 3 suitable (25%); 28% across all jobs; 23% for specialist roles. https://iab-forum.de/iab-stellenerhebung-2-2026-fast-drei-von-vier-bewerbungen-sind-aus-betrieblicher-sicht-ungeeignet/
QA | Application → qualified (baseline, all channels) | Automation | 25% | % | Researched | IAB 2026 chart: production jobs get 12 applications per vacancy, 3 suitable (25%); 28% across all jobs; 23% for specialist roles. https://iab-forum.de/iab-stellenerhebung-2-2026-fast-drei-von-vier-bewerbungen-sind-aus-betrieblicher-sicht-ungeeignet/
QS | Application → qualified (baseline, all channels) | Supervisors | 23% | % | Researched | IAB 2026 chart: production jobs get 12 applications per vacancy, 3 suitable (25%); 28% across all jobs; 23% for specialist roles. https://iab-forum.de/iab-stellenerhebung-2-2026-fast-drei-von-vier-bewerbungen-sind-aus-betrieblicher-sicht-ungeeignet/
PE | Qualified → passed assessment | Electricians | 50% | % | Own estimate | Gem 2025: ~35% of candidates brought onsite get offers (mostly US tech). Set higher (50%) because only pre-qualified people reach this step. https://lp.gem.com/rs/972-IVV-330/images/2025%20Recruiting%20Benchmarks%20-%20Gem.pdf
PM | Qualified → passed assessment | Mechatronics | 55% | % | Own estimate | Gem 2025: ~35% of onsite candidates get offers. Set at 55%: most common trade, the assessment is routine for it. https://lp.gem.com/rs/972-IVV-330/images/2025%20Recruiting%20Benchmarks%20-%20Gem.pdf
PA | Qualified → passed assessment | Automation | 45% | % | Own estimate | Gem 2025: ~35% of onsite candidates get offers. Set at 45%: PLC skills are tested hard. https://lp.gem.com/rs/972-IVV-330/images/2025%20Recruiting%20Benchmarks%20-%20Gem.pdf
PS | Qualified → passed assessment | Supervisors | 40% | % | Own estimate | Gem 2025: ~35% of onsite candidates get offers. Set at 40%: leadership is assessed on top of trade skills. https://lp.gem.com/rs/972-IVV-330/images/2025%20Recruiting%20Benchmarks%20-%20Gem.pdf
OE | Passed → offer made | Electricians | 90% | % | Own estimate | My estimate: ~10% drop out after passing (references, pay, shifts), 15% for supervisors. No public figure exists.
OM | Passed → offer made | Mechatronics | 90% | % | Own estimate | My estimate: ~10% drop out after passing (references, pay, shifts), 15% for supervisors. No public figure exists.
OA | Passed → offer made | Automation | 90% | % | Own estimate | My estimate: ~10% drop out after passing (references, pay, shifts), 15% for supervisors. No public figure exists.
OS | Passed → offer made | Supervisors | 85% | % | Own estimate | My estimate: ~10% drop out after passing (references, pay, shifts), 15% for supervisors. No public figure exists.
AE | Offer → signed contract | Electricians | 70% | % | Own estimate | Königsteiner 2022: 47% accepted vs 14% declined after an offer → ~77% acceptance. I use 70–75%: shift work and competing offers. https://www.lebensmittelzeitung.net/handel/karriere/rekrutierung-bewerber-sagen-haeufiger-ab-166449
AM | Offer → signed contract | Mechatronics | 75% | % | Own estimate | Königsteiner 2022: 47% accepted vs 14% declined after an offer → ~77% acceptance. I use 70–75%: shift work and competing offers. https://www.lebensmittelzeitung.net/handel/karriere/rekrutierung-bewerber-sagen-haeufiger-ab-166449
AA | Offer → signed contract | Automation | 70% | % | Own estimate | Königsteiner 2022: 47% accepted vs 14% declined after an offer → ~77% acceptance. I use 70–75%: shift work and competing offers. https://www.lebensmittelzeitung.net/handel/karriere/rekrutierung-bewerber-sagen-haeufiger-ab-166449
AS | Offer → signed contract | Supervisors | 70% | % | Own estimate | Königsteiner 2022: 47% accepted vs 14% declined after an offer → ~77% acceptance. I use 70–75%: shift work and competing offers. https://www.lebensmittelzeitung.net/handel/karriere/rekrutierung-bewerber-sagen-haeufiger-ab-166449
4. Budget policy and weekly phasing (Part 2)
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
B1 | Reserve held back (share of total budget) | All | 15% | % | Own estimate | 15% buffer, in the 10–20% range used for risky projects; released only on results. https://mastt.com/blogs/construction-contingency
B2 | Test tranche: first spend in every paid CPC/CPA channel × role cell, in weeks 1–2 | Paid CPC/CPA cells | 750 | € | Own estimate | €750 per paid channel and role in weeks 1–2: enough to see whether it works before spending more.
B4 | Share of test tranches spent in week 1 (rest in week 2) | Paid CPC/CPA cells | 40% | % | Own estimate | Week 1 has fewer assessment days, so 40% of the test money goes there.
B5 | Rounding step for the recommended budget | All | 2500 | € | Own estimate | Rounded up to a clean figure; the difference goes to the reserve.
B3 | Budget cut scenario the client asked about | All | 30% | % | Given | From the brief.
W1 | Share of media spend in week 1 | All paid | 31.6% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W2 | Share of media spend in week 2 | All paid | 13.1% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W3 | Share of media spend in week 3 | All paid | 16.1% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W4 | Share of media spend in week 4 | All paid | 17% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W5 | Share of media spend in week 5 | All paid | 19.5% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W6 | Share of media spend in week 6 | All paid | 2.7% | % | Own estimate | Paced so each week's qualified applicants fit the slots they can use (assessed 6 days after applying). Week 1 is biggest: it also fills the first assessment days (22–25 Oct). Week 6 is small: only 24 Nov is still useful.
W7 | Share of media spend in week 7 | All paid | 0% | % | Own estimate | No spend after the last useful application date.
W8 | Share of media spend in week 8 | All paid | 0% | % | Own estimate | No spend after the last useful application date.
W9 | Share of media spend in week 9 | All paid | 0% | % | Own estimate | No spend after the last useful application date.
W10 | Share of media spend in week 10 | All paid | 0% | % | Own estimate | No spend after the last useful application date.
W11 | Share of media spend in week 11 | All paid | 0% | % | Own estimate | No spend after the last useful application date.
S1 | Stress size for sensitivity test | All | 30% | % | Given | From the brief.
5. Talent pool sanity check (Part 2.2)
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
PSE | Qualified people employed within 75 km (Berlin + ~60% of Brandenburg) | Electricians | 4800 | people | Own estimate | BA employment, KldB 2625 + 2622: Berlin 2,708 + 60% of Brandenburg 3,417 (own scaling: ~60% of Brandenburg lies within 75 km) ≈ 4,800. Berlin file: https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-11-0-202512-xlsx.xlsx?__blob=publicationFile https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-12-0-202512-xlsx.xlsx?__blob=publicationFile
PSM | Qualified people employed within 75 km (Berlin + ~60% of Brandenburg) | Mechatronics | 26400 | people | Own estimate | BA employment, KldB 2611 + 2510/2511/2513 (skilled level): Berlin 17,490 + 60% of Brandenburg 14,878 (own scaling: ~60% of Brandenburg lies within 75 km) ≈ 26,400. Berlin file: https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-11-0-202512-xlsx.xlsx?__blob=publicationFile https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-12-0-202512-xlsx.xlsx?__blob=publicationFile
PSA | Qualified people employed within 75 km (Berlin + ~60% of Brandenburg) | Automation | 2000 | people | Own estimate | BA employment, KldB 2612: Berlin 1,254 + 60% of Brandenburg 1,206 (own scaling: ~60% of Brandenburg lies within 75 km) ≈ 2,000. Berlin file: https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-11-0-202512-xlsx.xlsx?__blob=publicationFile https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-12-0-202512-xlsx.xlsx?__blob=publicationFile
PSS | Qualified people employed within 75 km (Berlin + ~60% of Brandenburg) | Supervisors | 2200 | people | Own estimate | BA employment, supervisor codes 2519 + 2619 + 2629 + 2639: Berlin 1,494 + 60% of Brandenburg 1,209 (own scaling: ~60% of Brandenburg lies within 75 km) ≈ 2,200. Berlin file: https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-11-0-202512-xlsx.xlsx?__blob=publicationFile https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-12-0-202512-xlsx.xlsx?__blob=publicationFile
PIE | Share in-market or persuadable during the 6-week window | Electricians | 11% | % | Researched | Gallup 2024: active job search is 3% / 10% / 23% for high / low / no engagement; weighted by the 9% / 78% / 13% shares ≈ 11%. https://gallup.com/file/de/657716/Engagement-Index-Deutschland-Report-2024.pdf
PIM | Share in-market or persuadable during the 6-week window | Mechatronics | 11% | % | Researched | Gallup 2024: active job search is 3% / 10% / 23% for high / low / no engagement; weighted by the 9% / 78% / 13% shares ≈ 11%. https://gallup.com/file/de/657716/Engagement-Index-Deutschland-Report-2024.pdf
PIA | Share in-market or persuadable during the 6-week window | Automation | 11% | % | Researched | Gallup 2024: active job search is 3% / 10% / 23% for high / low / no engagement; weighted by the 9% / 78% / 13% shares ≈ 11%. https://gallup.com/file/de/657716/Engagement-Index-Deutschland-Report-2024.pdf
PIS | Share in-market or persuadable during the 6-week window | Supervisors | 11% | % | Researched | Gallup 2024: active job search is 3% / 10% / 23% for high / low / no engagement; weighted by the 9% / 78% / 13% shares ≈ 11%. https://gallup.com/file/de/657716/Engagement-Index-Deutschland-Report-2024.pdf
PRE | Qualified people elsewhere in Germany willing to relocate in the window | Electricians | 41 | people | Own estimate | Own sizing: few trades workers move across Germany for a job; national headcount × yearly move rate × share moving to Berlin-Brandenburg.
PRM | Qualified people elsewhere in Germany willing to relocate in the window | Mechatronics | 28 | people | Own estimate | Own sizing: few trades workers move across Germany for a job; national headcount × yearly move rate × share moving to Berlin-Brandenburg.
PRA | Qualified people elsewhere in Germany willing to relocate in the window | Automation | 16 | people | Own estimate | Own sizing: few trades workers move across Germany for a job; national headcount × yearly move rate × share moving to Berlin-Brandenburg.
PRS | Qualified people elsewhere in Germany willing to relocate in the window | Supervisors | 4 | people | Own estimate | Own sizing: few trades workers move across Germany for a job; national headcount × yearly move rate × share moving to Berlin-Brandenburg.
6. Week-by-week money rules (Part 4) — used by the Tracker tab
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
R1 | Minimum spend before judging a cell | Per cell | 500 | € | Own estimate | Don't judge a channel on less than €500 or 30 applications; too little data.
R2 | …or minimum applications before judging a cell | Per cell | 30 | apps | Own estimate | Don't judge a channel on less than €500 or 30 applications; too little data.
R3 | Scale up when re-forecast cost per qualified ≤ this × plan | Per cell | 0.8 | × plan | Own estimate | 20% cheaper than plan and slots free → scale up.
R4 | Cut budget 50% when re-forecast cost per qualified ≥ this × plan | Per cell | 1.5 | × plan | Own estimate | A common ad rule is 'reduce if cost is 1.2–2× target' (roaspig); I halve at 1.5×. https://roaspig.com/blog/automated-rules-manage-meta-budgets/
R5 | Switch off when cost per qualified ≥ this × plan | Per cell | 2 | × plan | Own estimate | Twice the plan cost → switch off (common ad practice). https://roaspig.com/blog/automated-rules-manage-meta-budgets/
R6 | …or switch off when spend reaches this and R2 applications brought zero qualified | Per cell | 750 | € | Own estimate | Test spent (€750) and 30+ applications with none qualified → off. By chance that happens < 0.1% of the time for job boards (~22–25% qualify: 0.775^30) and ~4% for Meta (~10% qualify: 0.9^30).
TP1 | Initiative test: PASS needs about this share of planned qualified in the window (rounded down) | Initiatives | 60% | % | Own estimate | Two-week test passes at about 60% of the planned qualified applicants (rounded down to a whole person, so 54–58% at the current plan).
TP2 | Initiative test: PASS needs cost per qualified ≤ this × plan | Initiatives | 1.5 | × plan | Own estimate | Same cost limit as the channel cut rule (1.5× plan).
TK1 | Initiative test: KILL if qualified below this share of plan | Initiatives | 30% | % | Own estimate | Kill the initiative if fewer than about 30% of the planned qualified arrive (rounded up to a whole person).
TK2 | Initiative test: KILL if cost per qualified above this × plan | Initiatives | 2 | × plan | Own estimate | Same cost limit as the channel switch-off rule (2× plan).
I1W1 | I1a re-applications arriving in week 1 (waves on days 2 and 7) | Rediscovery | 60% | % | Own estimate | Most replies come within a day of each message (Pin 2026), so 60% arrive in week 1. https://www.pin.com/blog/recruiting-outreach-benchmark-report/
I1W2 | I1a re-applications arriving in week 2 | Rediscovery | 29% | % | Own estimate | Most replies come within a day of each message (Pin 2026), so 60% arrive in week 1. https://www.pin.com/blog/recruiting-outreach-benchmark-report/
I1W3 | I1a re-applications arriving in week 3 | Rediscovery | 11% | % | Own estimate | Most replies come within a day of each message (Pin 2026), so 60% arrive in week 1. https://www.pin.com/blog/recruiting-outreach-benchmark-report/
R7 | Scale-up step per week | Per cell | 25% | % | Own estimate | Between the common +20% and +30% scale-up rules (roaspig). https://roaspig.com/blog/automated-rules-manage-meta-budgets/
R9 | Minimum interviews done before using the actual pass rate | Per role | 10 | interviews | Own estimate | Switch to the real pass rate after 10 interviews.
R10 | Minimum offers before using the actual acceptance rate | Per role | 5 | offers | Own estimate | Switch to the real acceptance rate after 5 offers.
F1 | Pool flag: 'very hard' when the plan needs more than this share of the reachable pool | Funnel pool check | 25% | % | Own estimate | Display flag only: the plan needs over a quarter of everyone reachable.
F2 | Pool flag: 'tight' above this share | Funnel pool check | 12% | % | Own estimate | Display flag only: the plan needs over 1 in 8 of everyone reachable.
F3 | Capacity flag: 'tight' when slot use exceeds | Funnel / Weekly | 85% | % | Own estimate | Risk rises once capacity is more than 85% used (Bagust et al., BMJ 1999). https://pubmed.ncbi.nlm.nih.gov/10406748/
F4 | Weekly flag: 'full' when a week's slot use exceeds | Weekly | 90% | % | Own estimate | Above 90% use, shortages become regular (same study), so the week counts as full. https://pubmed.ncbi.nlm.nih.gov/10406748/
R13 | Pacing floor: release reserve to the cheapest cells with capacity when next week's forecast qualified falls below | All roles | 50 | qualified/wk | Own estimate | Next week below 90% of the 55 slots → release reserve to the cheapest working channel.
6a. Facts behind channel quality and volumes (cells in black below are calculated from these)
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
CXB | Channel quality index: online job boards (programmatic, StepStone, LinkedIn) | Channels | 0.9 | × | Researched | Derived from IAB 2025: decisive ÷ used for job boards (21% ÷ 57% = 0.37) ÷ 0.41 = 0.90. Average = mean of decisive ÷ used over the three channels IAB reports (homepage 20/70, job boards 21/57, personal contacts 27/48) = 0.41. https://iab-forum.de/online-medien-sind-bei-der-personalsuche-auf-dem-vormarsch/
CXH | Channel quality index: own careers page (organic, Google Search ads) | Channels | 0.7 | × | Researched | Derived from IAB 2025: decisive ÷ used for the employer homepage (20% ÷ 70% = 0.29) ÷ 0.41 = 0.70. Average = mean of decisive ÷ used over the three channels IAB reports (homepage 20/70, job boards 21/57, personal contacts 27/48) = 0.41. https://iab-forum.de/online-medien-sind-bei-der-personalsuche-auf-dem-vormarsch/
CXS | Channel quality index: social media (Meta) | Channels | 0.41 | × | Researched | Derived from IAB data (2022): social media was used for 42% of filled jobs but decisive for 1 in 14; (7.1% ÷ 42%) ÷ 0.41 ≈ 0.41. https://ohn.haendlerbund.de/themen/unternehmen-maerkte/139538-social-media-whatsapp-mitarbeitersuche-immer-wichtiger
RXP | Reach: share of skilled-worker job seekers using Indeed (programmatic cap) | Channels | 36% | % | Researched | 36% of skilled-worker job seekers use Indeed (Trendence 2023). https://www.personalwirtschaft.de/?p=157882
RXL | Reach: share of skilled-worker job seekers using LinkedIn | Channels | 15% | % | Researched | 15% of skilled-worker job seekers use LinkedIn (Trendence 2023). https://www.personalwirtschaft.de/?p=157882
RXG | Reach: share of job seekers starting their search on Google | Channels | 10.5% | % | Researched | 10.5% of job seekers start their search on Google (softgarden). https://www.personalwirtschaft.de/news/recruiting/jeder-zehnte-nutzt-google-zur-jobsuche-97400/
APV | Applications per vacancy, firms with 250+ staff | Organic | 27 | apps | Researched | Firms with 250+ staff get ~27 applications per vacancy (IAB 2026). https://iab-forum.de/iab-stellenerhebung-2-2026-fast-drei-von-vier-bewerbungen-sind-aus-betrieblicher-sicht-ungeeignet/
CPS | Share of applications that come via the careers page | Organic | 13% | % | Researched | 13% of applications come through the careers page (CareerPlug 2025). https://www.careerplug.com/wp-content/uploads/2025/04/Recruiting-Metrics-Report.pdf
RDE | Qualified applications per Elektroniker social campaign (median) | Meta electricians | 20 | qualified | Researched | Typical social campaign for electricians brings ~20 qualified applications (Redline, 181 campaigns). https://redline-grow.de/bewerbungen-pro-stelle
RDM | Qualified applications per Kfz-Mechatroniker social campaign (median) | Meta mechatronics | 23 | qualified | Researched | Typical social campaign for mechatronics brings ~23 qualified applications (Redline). https://redline-grow.de/bewerbungen-pro-stelle
RD2 | Qualified applications per Elektroniker social campaign (mean, sizes I2) | I2 | 29.5 | qualified | Researched | Redline 2024–26: mean 29.5 qualified applications per Elektroniker campaign (11 campaigns). https://redline-grow.de/bewerbungen-pro-stelle
SSW | Days one StepStone ad runs | StepStone | 30 | days | Researched | A StepStone ad runs 30 days. https://www.stepstone.de/e-recruiting/stellenanzeige-aufgeben/
STAFF | Plant headcount | I1 | 10703 | people | Researched | Plant headcount (Electrek, March 2026). https://electrek.co/2026/03/04/tesla-giga-berlin-ig-metall-union-vote-collapse/
MSH | Maintenance trades as share of production occupations | I1 | 7.8% | % | Researched | BA employment, Germany: maintenance codes 2513 + 2625 + 2611 + 2612 + supervisors 2519 + 2619 + 2629 (536,520) ÷ production occupations 21–29 (6,850,263) = 7.8%. Also applied to Polish industry for the I3 supply check (my estimate; an upper bound). https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-d-0-202512-xlsx.xlsx?__blob=publicationFile
TURN | Annual staff turnover, Brandenburg firms | I1 | 12% | % | Researched | IAB-Betriebspanel Brandenburg: ~6% of jobs ended in the first half of 2024 → ~12% a year. https://mweke.brandenburg.de/media/bb1.a.3814.de/Betriebspanel%20Brandenburg%202024%20-%20final.pdf
REFSH | Share of hires that come from referrals | I1 | 11% | % | Researched | Referrals bring ~11% of hires (CareerPlug 2025). https://www.careerplug.com/wp-content/uploads/2025/04/Recruiting-Metrics-Report.pdf
PLI | Industry workers (NACE B–E) in the Polish border regions Lubuskie + Zachodniopomorskie, 2025 | I3 | 237500 | people | Researched | Eurostat lfst_r_lfe2en2, 2025: Lubuskie (PL43) 97.0k + Zachodniopomorskie (PL42) 140.5k employed in industry B–E (https://ec.europa.eu/eurostat/databrowser/view/lfst_r_lfe2en2/default/table).
PLC | Polish cross-border commuters working in Brandenburg (all jobs) | I3 | 13775 | people | Researched | IAB-Regional Berlin-Brandenburg 1/2020, table 3 (BA data, June 2019): 13,775 commuters from Poland to Brandenburg workplaces (https://doku.iab.de/regional/BB/2020/regional_bb_0120.pdf).
PLT | …of which in machine/vehicle, metalworking and building trades | I3 | 1678 | people | Researched | Same table: machine and vehicle technology 825 + metal 424 + building construction 429 = 1,678 (https://doku.iab.de/regional/BB/2020/regional_bb_0120.pdf).
7. Channel × role inputs (Part 2.2). Basis: CPC → CPA = CPC ÷ click-to-apply rate; CPA = bought per application/lead; Slot = fixed-price 30-day ad → CPA = price ÷ apps per ad; Free = no media cost.
ID | Channel | Role | Basis | Unit cost € (CPC / CPA / slot price) | Click→apply % or apps per slot | Share qualified | Max applications over campaign (or no. of slots) | Downstream adj. (× role conversion) | Fixed cost € | Label | Source / reasoning
C01 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Electricians | Free | 0 |  | 17.5% | 105 | 1 | 0 | Researched | Free listings (careers site, BA Jobbörse, Google for Jobs). Volume: ~27 applications per vacancy, 13% via the careers page. https://www.arbeitsagentur.de/faktor-a/mitarbeiter-finden/so-funktioniert-deutschlands-groesste-jobboerse
C02 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Mechatronics | Free | 0 |  | 17.5% | 158 | 1 | 0 | Researched | Free listings (careers site, BA Jobbörse, Google for Jobs). Volume: ~27 applications per vacancy, 13% via the careers page. https://www.arbeitsagentur.de/faktor-a/mitarbeiter-finden/so-funktioniert-deutschlands-groesste-jobboerse
C03 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Automation | Free | 0 |  | 17.5% | 53 | 1 | 0 | Researched | Free listings (careers site, BA Jobbörse, Google for Jobs). Volume: ~27 applications per vacancy, 13% via the careers page. https://www.arbeitsagentur.de/faktor-a/mitarbeiter-finden/so-funktioniert-deutschlands-groesste-jobboerse
C04 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Supervisors | Free | 0 |  | 16.1% | 35 | 1 | 0 | Researched | Free listings (careers site, BA Jobbörse, Google for Jobs). Volume: ~27 applications per vacancy, 13% via the careers page. https://www.arbeitsagentur.de/faktor-a/mitarbeiter-finden/so-funktioniert-deutschlands-groesste-jobboerse
C05 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Electricians | CPA | 161 |  | 22.5% | 910 | 1 | 0 | Researched | Indeed's CPA median is €161 in TalentBait's DACH 2024–26 dataset (2,549 channel-campaigns across all channels), used as the programmatic proxy. Volume capped by Indeed's reach. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C06 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Mechatronics | CPA | 161 |  | 22.5% | 4690 | 1 | 0 | Researched | Indeed's CPA median is €161 in TalentBait's DACH 2024–26 dataset (2,549 channel-campaigns across all channels), used as the programmatic proxy. Volume capped by Indeed's reach. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C07 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Automation | CPA | 161 |  | 22.5% | 380 | 1 | 0 | Researched | Indeed's CPA median is €161 in TalentBait's DACH 2024–26 dataset (2,549 channel-campaigns across all channels), used as the programmatic proxy. Volume capped by Indeed's reach. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C08 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Supervisors | CPA | 161 |  | 20.7% | 430 | 1 | 0 | Researched | Indeed's CPA median is €161 in TalentBait's DACH 2024–26 dataset (2,549 channel-campaigns across all channels), used as the programmatic proxy. Volume capped by Indeed's reach. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C09 | StepStone (30-day single ad) | Electricians | Slot | 1449 | 12 | 22.5% | 2 | 1 | 0 | Own estimate | Own estimate: from €1,449 per 30-day ad (StepStone price list); StepStone says HR teams get ~12 applications per vacancy across all channels, used here as applications per ad. https://www.stepstone.de/e-recruiting/stellenanzeige-aufgeben/ https://www.stepstone.de/e-recruiting/hr-wissen/recruiting/bewerberqualitaet-steigern
C10 | StepStone (30-day single ad) | Mechatronics | Slot | 1449 | 12 | 22.5% | 2 | 1 | 0 | Own estimate | Own estimate: from €1,449 per 30-day ad (StepStone price list); StepStone says HR teams get ~12 applications per vacancy across all channels, used here as applications per ad. https://www.stepstone.de/e-recruiting/stellenanzeige-aufgeben/ https://www.stepstone.de/e-recruiting/hr-wissen/recruiting/bewerberqualitaet-steigern
C11 | StepStone (30-day single ad) | Automation | Slot | 1449 | 12 | 22.5% | 2 | 1 | 0 | Own estimate | Own estimate: from €1,449 per 30-day ad (StepStone price list); StepStone says HR teams get ~12 applications per vacancy across all channels, used here as applications per ad. https://www.stepstone.de/e-recruiting/stellenanzeige-aufgeben/ https://www.stepstone.de/e-recruiting/hr-wissen/recruiting/bewerberqualitaet-steigern
C12 | StepStone (30-day single ad) | Supervisors | Slot | 1449 | 12 | 20.7% | 1 | 1 | 0 | Own estimate | Own estimate: from €1,449 per 30-day ad (StepStone price list); StepStone says HR teams get ~12 applications per vacancy across all channels, used here as applications per ad. https://www.stepstone.de/e-recruiting/stellenanzeige-aufgeben/ https://www.stepstone.de/e-recruiting/hr-wissen/recruiting/bewerberqualitaet-steigern
C13 | LinkedIn (promoted jobs + InMail) | Automation | CPA | 96 |  | 22.5% | 160 | 1 | 0 | Researched | DACH median €96 per application (TalentBait). Used only for automation and supervisors. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C14 | LinkedIn (promoted jobs + InMail) | Supervisors | CPA | 96 |  | 20.7% | 180 | 1 | 0 | Researched | DACH median €96 per application (TalentBait). Used only for automation and supervisors. https://www.talentbait.de/recruiting-kanaele-uebersicht/
C15 | Meta social (FB/IG lead ads, 75 km geo) | Electricians | CPA | 84 |  | 10.25% | 200 | 1 | 0 | Own estimate | Own estimate: TalentBait's example ad shows ~€84 per application for trades (its measured averages: €52 raw, €104 per qualified); volume from Redline campaign data. https://www.talentbait.de/social-media-recruiting
C16 | Meta social (FB/IG lead ads, 75 km geo) | Mechatronics | CPA | 84 |  | 10.25% | 220 | 1 | 0 | Own estimate | Own estimate: TalentBait's example ad shows ~€84 per application for trades (its measured averages: €52 raw, €104 per qualified); volume from Redline campaign data. https://www.talentbait.de/social-media-recruiting
C17 | Google Search ads (job-intent keywords) | Electricians | CPA | 179 |  | 17.5% | 340 | 1 | 0 | Researched | Google Search ads ~€179 per application, low volume (TalentBait). https://www.talentbait.de/recruiting-kanaele-uebersicht/
C18 | Google Search ads (job-intent keywords) | Mechatronics | CPA | 179 |  | 17.5% | 1760 | 1 | 0 | Researched | Google Search ads ~€179 per application, low volume (TalentBait). https://www.talentbait.de/recruiting-kanaele-uebersicht/
C19 | Google Search ads (job-intent keywords) | Automation | CPA | 179 |  | 17.5% | 140 | 1 | 0 | Researched | Google Search ads ~€179 per application, low volume (TalentBait). https://www.talentbait.de/recruiting-kanaele-uebersicht/
C20 | Google Search ads (job-intent keywords) | Supervisors | CPA | 179 |  | 16.1% | 160 | 1 | 0 | Researched | Google Search ads ~€179 per application, low volume (TalentBait). https://www.talentbait.de/recruiting-kanaele-uebersicht/
8. New-initiative inputs (Part 3) — maths on the Initiatives tab
ID | Parameter | Role / scope | Value | Unit | Label | Source / reasoning
I1RE | I1: past applicants in client ATS who were qualified but not hired (last 12 months) | Electricians | 65 | records | Own estimate | Calculated: last year's maintenance hires (STAFF × MSH × TURN × this role's share) × qualified runners-up per hire (1 ÷ qualified→signed − 1). Replaced by the real export on day 1.
I1RM | I1: past applicants in client ATS who were qualified but not hired (last 12 months) | Mechatronics | 76 | records | Own estimate | Calculated: last year's maintenance hires (STAFF × MSH × TURN × this role's share) × qualified runners-up per hire (1 ÷ qualified→signed − 1). Replaced by the real export on day 1.
I1RA | I1: past applicants in client ATS who were qualified but not hired (last 12 months) | Automation | 38 | records | Own estimate | Calculated: last year's maintenance hires (STAFF × MSH × TURN × this role's share) × qualified runners-up per hire (1 ÷ qualified→signed − 1). Replaced by the real export on day 1.
I1RS | I1: past applicants in client ATS who were qualified but not hired (last 12 months) | Supervisors | 32 | records | Own estimate | Calculated: last year's maintenance hires (STAFF × MSH × TURN × this role's share) × qualified runners-up per hire (1 ÷ qualified→signed − 1). Replaced by the real export on day 1.
I1C | I1: share of re-contacted past applicants who re-apply | All | 12% | % | Own estimate | Cold outreach gets ~5% replies (Pin 2026); past applicants already know the employer, so I assume 12%. https://www.pin.com/blog/recruiting-outreach-benchmark-report/
I1Q | I1: share qualified among re-applicants | All | 50% | % | Own estimate | They met the requirements once; I assume half still do (Forrester via SHRM: most remain a 70%+ match). https://www.shrm.org/mena/topics-tools/news/technology/talent-rediscovery-tools-help-address-labor-shortages
I1FE | I1: employee-referred applications over campaign | Electricians | 20 | apps | Own estimate | Calculated: referrals give REFSH (11%) of this role's hires: REFSH × openings ÷ (I1FQ × qualified→signed × I1A).
I1FM | I1: employee-referred applications over campaign | Mechatronics | 26 | apps | Own estimate | Calculated: referrals give REFSH (11%) of this role's hires: REFSH × openings ÷ (I1FQ × qualified→signed × I1A).
I1FA | I1: employee-referred applications over campaign | Automation | 11 | apps | Own estimate | Calculated: referrals give REFSH (11%) of this role's hires: REFSH × openings ÷ (I1FQ × qualified→signed × I1A).
I1FS | I1: employee-referred applications over campaign | Supervisors | 9 | apps | Own estimate | Calculated: referrals give REFSH (11%) of this role's hires: REFSH × openings ÷ (I1FQ × qualified→signed × I1A).
I1FQ | I1: share qualified among referrals | All | 45% | % | Own estimate | Referred applicants are better pre-filtered (IAB: referrals are the most decisive channel), so 45% qualify. https://iab-forum.de/online-medien-sind-bei-der-personalsuche-auf-dem-vormarsch/
I1M | I1: messaging cost per contacted past applicant (email + SMS tool) | All | 0.3 | € | Own estimate | Three text messages at ~€0.075 each (seven.io price list, 2016 rates) plus email, rounded up to €0.30. https://www.seven.io/en/prices/
I1B | I1: referral bonus per signed referred hire (paid from this budget) | All | 1000 | € | Researched | Most firms pay €501–1,000 per successful referral (Radancy survey, 335 firms worldwide). https://www.personalwirtschaft.de/?p=166393
I1A | I1: downstream adjustment (pass/accept better than average) | All | 1.15 | × | Own estimate | Referred and known candidates pass and accept a little more often (+15%). https://www.metaview.ai/resources/blog/do-referred-candidates-interview-better
I2P | I2: construction/Handwerk electricians (Elektroniker Energie- und Gebäudetechnik) within 75 km | Electricians | 10000 | people | Own estimate | BA employment, KldB 2621 Bauelektrik: Berlin 6,204 + 60% of Brandenburg 5,905 (own scaling: ~60% of Brandenburg lies within 75 km) ≈ 10,000. Berlin file: https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-11-0-202512-xlsx.xlsx?__blob=publicationFile https://statistik.arbeitsagentur.de/Statistikdaten/Detail/202512/iiia6/beschaeftigung-sozbe-bo-heft/bo-heft-12-0-202512-xlsx.xlsx?__blob=publicationFile
I2S | I2: share who apply over the campaign (reachable × persuaded) | Electricians | 1.18% | % | Own estimate | Calculated: RD2 (Redline, ~30 qualified per electrician campaign) ÷ I2Q ÷ I2P.
I2C | I2: cost per application (Meta/Google + 6-question quiz funnel) | Electricians | 84 | € | Own estimate | Own estimate: TalentBait's example ad shows ~€84 per application for trades; its measured averages are €52 per raw application and €104 per qualified one. https://www.talentbait.de/social-media-recruiting
I2Q | I2: share qualified (only if client accepts EGT + Elektrofachkraft + 2 yrs, with in-house bridge) | Electricians | 25% | % | Own estimate | Calculated: same as electricians (25%), because the quiz admits only certified electricians.
I2A | I2: downstream adjustment (industrial skills gap) | Electricians | 0.9 | × | Own estimate | They lack PLC skills, so they pass like automation candidates: 45% ÷ 50% = 0.9.
I2F | I2: fixed set-up cost (German copywriter + quiz-funnel tool, 3 months) | Electricians | 1200 | € | Own estimate | Copywriter (~11 hours at €65) plus a quiz tool for 3 months. https://www.freelancermap.de/freelancer/texterstellung
I3C | I3: blended cost per application, Pracuj.pl + OLX Praca + Polish-geo Meta | Mechatronics | 14 | € | Own estimate | Pracuj.pl ad price divided by expected applications, blended with OLX and Meta. https://dlafirm.pracuj.pl/cennik-uslug/pakiety-ogloszen
I3Q | I3: share qualified after Polish-language pre-screen call | Mechatronics | 14% | % | Own estimate | Own estimate: the Polish ads carry trade knock-out questions (certificate, shifts), so language is the binding filter. Eurostat AES 2022, Poland, ages 25–64, vocational upper-secondary: 58.7% know a foreign language (edat_aes_l23) × 23.6% of them good or proficient (edat_aes_l33) ≈ 14%. https://ec.europa.eu/eurostat/databrowser/view/edat_aes_l23/default/table https://ec.europa.eu/eurostat/databrowser/view/edat_aes_l33/default/table
I3X | I3: max applications over campaign | Mechatronics | 350 | apps | Own estimate | Calculated: the applications needed to fill the 40% Polish cap.
I3A | I3: downstream adjustment (pre-screened) | Mechatronics | 1 | × | Own estimate | No pass-rate uplift assumed for the pre-screen; none has been measured.
I3H | I3: pre-screen call time per Polish applicant | Mechatronics | 15 | minutes | Researched | Phone screens take 15–30 minutes (Indeed); a checklist call takes 15. https://www.indeed.com/hire/c/info/what-is-a-phone-screen
I3W | I3: pre-screener hourly rate | Mechatronics | 19 | € | Researched | Polish freelance recruiters charge ~€14–19 an hour. https://rocketjobs.pl/oferta-pracy/intent-tech-recruiter-freelance--warszawa-hr-recruitment-9e0cdcee
I3T | I3: Polish translation of job ads + landing page | Mechatronics | 400 | € | Own estimate | Translation at the German statutory rate per line (JVEG). https://www.gesetze-im-internet.de/jveg/__11.html
I2W | I2: bridge course after signing (weeks, run by the client's maintenance trainers) | Electricians | 3 | weeks | Own estimate | 2–4 weeks to cover the PLC/industrial gap; onboarding time paid as salary, so outside the campaign budget. Client names a trainer by 23 Oct.
I2L | I2: days from campaign start to go-live (ads, quiz, German copy) | Electricians | 3 | days | Own estimate | Setup plan: copy and quiz written in 2 days, client profile sign-off, live Fri 23 Oct.
I3L | I3: days from campaign start to go-live (translation, freelancer hired) | Mechatronics | 7 | days | Own estimate | Setup plan: Polish translation and hiring the freelancer take a week, live Tue 27 Oct.

## Funnel
Part 1 — Funnel by role (work back from openings)
How: qualified needed = openings ÷ (pass × offer × accept); applications needed = qualified ÷ share qualified. Rates from Assumptions §3. 'Qualified' = right trade qualification + English or German + accepts shifts (brief).
Role | Openings | App → qualified | Qualified → passed | Passed → offer | Offer → signed | Qualified → signed | App → signed | Offers needed | Passed needed | Qualified needed | Applications needed (baseline Q) | Applications in plan (channel mix) | Blended Q in plan | Qualified in plan | Share of assessment slots
Electricians | 30 | 25% | 50% | 90% | 70% | 31.5% | 7.875% | 42.8571 | 47.619 | 95.2381 | 380.9524 | 414.2726 | 23.23% | 96.2531 | 30.63%
Mechatronics | 45 | 25% | 55% | 90% | 75% | 37.12% | 9.281% | 60 | 66.6667 | 121.2121 | 484.8485 | 662.4693 | 17.93% | 118.7731 | 37.79%
Automation | 15 | 25% | 45% | 90% | 70% | 28.35% | 7.087% | 21.4286 | 23.8095 | 52.9101 | 211.6402 | 226.4713 | 22.88% | 51.8256 | 16.49%
Supervisors | 10 | 23% | 40% | 85% | 70% | 23.8% | 5.474% | 14.2857 | 16.8067 | 42.0168 | 182.6818 | 191.362 | 21.49% | 41.1213 | 13.08%
Total | 100 |  |  |  |  | 32.12% |  | 138.5714 | 154.902 | 311.3771 | 1260.1228 | 1494.5752 | 20.61% | 307.9731 | 97.99%
Qualified needed (col K) uses role averages; 'Qualified in plan' (col O) reflects the actual channel mix incl. better/worse downstream conversion of initiatives. Capacity is checked on col O.
Timeline and recruiter capacity (Part 1.3)
First assessment date | 2026-10-22
Last signing date | 2026-12-18
Days assessment → signed (E/M/A) | 18
Days assessment → signed (Supervisors) | 25
Last assessment date (E/M/A) | 2026-11-30
Last assessment date (Supervisors) | 2026-11-23
Last useful application date (E/M/A) | 2026-11-24
Last useful application date (Supervisors) | 2026-11-17
Assessment window (days, E/M/A) | 40
Assessment slots available (capacity × weeks) | 314.2857
Qualified applicants in plan | 307.9731
Slot utilisation | 97.99% | Tight: little headroom
Hires per qualified applicant (plan mix) | 32.47%
Max hires the 55/week limit allows before 31 Dec | 102.0497 | If every slot is filled at the plan's conversion; above 100 = headroom.
Which role is hardest to fill? (Part 1.3)
Role | Openings | Qualified needed (plan) | Hire capacity of all channels at plan rates | Coverage (capacity ÷ openings) | Reachable qualified pool (pool check below) | Qualified needed ÷ reachable pool (excl. I2, pool check below) | Highest cost per hire we must buy (beyond tests) | Polish route allowed? | Foreign-trained route by 31 Dec? | Coverage without the unproven I2 initiative | Ranking helper (roles with openings)
Electricians | 30 | 96.2531 | 110.2216 | 3.6741 | 569 | 11.73% | 2271.6049 | No | No – recognition takes 2–4 months | 3.3953 | 3.3953
Mechatronics | 45 | 118.7731 | 551.6901 | 12.2598 | 2932 | 4.051% | 1927.4224 | Yes (≤40%) | Yes (no recognition gate in brief) | 12.2598 | 12.2598
Automation | 15 | 51.8256 | 47.9085 | 3.1939 | 236 | 21.96% | 1504.9971 | No | Yes (no recognition gate in brief) | 3.1939 | 3.1939
Supervisors | 10 | 41.1213 | 39.7495 | 3.9749 | 246 | 16.72% | 1948.6055 | No | Yes (no recognition gate in brief) | 3.9749 | 3.9749
Hardest role: Electricians (last hire costs €2,272), the highest in column H. Why: industrial electricians are the scarcest trade in Brandenburg (KOFA 2026: 85.7% of vacancies have no suitable unemployed candidate vs 41.4% overall, https://www.kofa.de/media/Publikationen/Laendersteckbriefe/Brandenburg.pdf), and they have no Polish or foreign-trained route under the brief. Automation’s pool and channel coverage are tighter (column G: 22% of reachable people vs 12%; column E: 3.2× vs 3.7×), but it needs only 15 hires and its last hire is cheaper, so it is watched in the weekly pool check rather than ranked hardest.
Sensitivity: each assumption 30% worse (Part 1.4)
Stress size: | 30%
Assumption made 30% worse | Qualified applicants needed | Slot utilisation | Hires possible before 31 Dec | Hires lost vs 100 | Spend needed (€, approx.: all variable spend scaled, channel caps ignored) | Change in media | Why
Base case | 307.9731 | 97.99% | 100 | 0 | 102255.8476 | 0% | Plan as built.
Qualified → signed (assessment pass rate) ×0.7 | 439.9615 | 140% | 71.4348 | 28.5652 | 146079.7822 | 42.86% | Each qualified applicant yields 30% fewer hires → 43% more qualified needed, but slots are fixed at 55/week.
Offer acceptance ×0.7 | 439.9615 | 140% | 71.4348 | 28.5652 | 146079.7822 | 42.86% | Same arithmetic as pass rate: it also sits between the capacity limit and the hire.
Application → qualified ×0.7 | 307.9731 | 97.99% | 100 | 0 | 146079.7822 | 42.86% | Costs 43% more per qualified; slots unaffected; channels run out sooner (electricians first).
Cost per application ×1.3 | 307.9731 | 97.99% | 100 | 0 | 132932.6018 | 30% | Pure money: +30% media, no effect on hires if the money is there.
Recruiter capacity ×0.7 (≈38/week), given in the brief, shown for context | 307.9731 | 140% | 71.4348 | 28.5652 | 102255.8476 | 0% | Fewer slots: hires capped by capacity. Not ranked: 55/week is given, not assumed.
Most sensitive assumption (largest hire loss; capacity excluded as it is given): |  |  | Qualified → signed (assessment pass rate) ×0.7
Pass rate and acceptance tie (29 hires lost each). I name the pass rate: it depends on this plant’s own test, so it is the least known, and it can only be read after interviews (week-2 check). Acceptance can be protected with fast offers. Why it matters: assessment capacity, not money, is the limit, so a lower pass rate or acceptance can’t be fixed by spending more; a lower share qualified or dearer clicks only cost money.
Talent-pool sanity check (Part 2.2): can the channels plausibly deliver the qualified applicants we plan?
Role | Employed within 75 km | Share in market / persuadable | Local reachable | Relocators | Reachable qualified pool | Qualified applicants in plan from this pool (excl. I2) | Plan ÷ pool | Max qualified all channels could deliver (excl. I2) | Channel max ÷ pool | Read-out
Electricians | 4800 | 11% | 528 | 41 | 569 | 66.7531 | 11.73% | 321.425 | 56.49% | Comfortable
Mechatronics | 26400 | 11% | 2904 | 28 | 2932 | 118.7731 | 4.051% | 1484.11 | 50.62% | Comfortable
Automation | 2000 | 11% | 220 | 16 | 236 | 51.8256 | 21.96% | 167.905 | 71.15% | Tight
Supervisors | 2200 | 11% | 242 | 4 | 246 | 41.1213 | 16.72% | 166.119 | 67.53% | Tight
Channel max can exceed the pool because the same people apply via several channels. Construction electricians (I2) are a separate pool and excluded here.

## Initiatives
Part 3 — New sources beyond the usual paid channels (maths feeds the Channels tab)
How: people reachable × share who apply = applications; × share qualified × qualified → signed = hires; cost ÷ hires = cost per hire.
I1 · Talent rediscovery (past applicants in client ATS) + employee referral sprint — built for electricians, used for all roles
Line | Electricians | Mechatronics | Automation | Supervisors | Total
I1a Past qualified applicants in ATS | 65 | 76 | 38 | 32 | 211
I1a Re-application rate | 12% | 12% | 12% | 12%
I1a Re-applications (max) | 7.8 | 9.12 | 4.56 | 3.84 | 25.32
I1a Share qualified | 50% | 50% | 50% | 50%
I1 Qualified → signed (role × adj.) | 36.23% | 42.69% | 32.6% | 27.37%
I1a Messaging cost (records × €/contact) | 19.5 | 22.8 | 11.4 | 9.6 | 63.3
I1a Cost per application (→ Channels) | 2.5 | 2.5 | 2.5 | 2.5 |  | ≈€2.50 per application: messaging is nearly free; the scarce input is the client’s ATS export.
I1a Hires if fully used | 1.4128 | 1.9468 | 0.74334 | 0.5255 | 4.6285
I1b Referral applications (max) | 20 | 26 | 11 | 9 | 66
I1b Share qualified | 45% | 45% | 45% | 45%
I1b Hires if fully used | 3.2603 | 4.9952 | 1.6138 | 1.1085 | 10.9777
I1b Referral bonuses at full use (hires × bonus) | 3260.25 | 4995.1687 | 1613.8238 | 1108.485 | 10977.7275
I1b Expected bonus cost per application (→ Channels) | 163.0125 | 192.1219 | 146.7113 | 123.165 |  | Bonus is only paid when a referred hire signs; shown per application so it ranks against paid channels.
I1 Total hires if fully used | 4.673 | 6.942 | 2.3572 | 1.634 | 15.6062
I1 Total cost if fully used | 3279.75 | 5017.9688 | 1625.2238 | 1118.085 | 11041.0275
I1 Cost per hire | 701.8473 | 722.8415 | 689.4836 | 684.2672 | 707.478
I2 · 'Vom Handwerk in die Industrie' — construction electricians → plant maintenance (electricians only)
Construction/Handwerk electricians within 75 km | 10000
Share who apply | 1.18%
Max applications | 118
Cost per application | 84
Share qualified (client accepts profile) | 25%
Qualified | 29.5
Qualified → signed (electrician rate × I2A adjustment) | 28.35%
Expected hires if fully used | 8.3633
Media at full use | 9912
Fixed set-up | 1200
Cost per hire at full use | 1328.6701
I3 · Polish border corridor with a remote Polish-speaking pre-screener (mechatronics only, ≤40% of those hires)
All-in cost per application (ads + pre-screen call) (→ Channels) | 18.75
Share qualified after pre-screen | 14%
Max applications | 350
Qualified → signed (mechatronics rate × I3A adjustment) | 37.12%
Hire cap from the 40% rule | 18
Hires if fully used (capped) | 18
Ad cost per application (Pracuj.pl, OLX Praca, PL-geo Meta) | 14
Pre-screen cost per applicant (minutes ÷ 60 × hourly rate) | 4.75
Fixed cost: translation | 400
Applications needed to hit the cap | 346.3203
Cost per hire at cap (incl. fixed) | 382.9726
Polish supply check: the border regions have ~18,525 maintenance-type workers (Eurostat 2025: 237,500 industry workers × the German BA maintenance share 7.8%, applied to Poland as my estimate; an upper bound, since whole regions and all industry staff are counted). The plan needs 346 applications = 1.9% of them, vs the 1.2% response assumed for construction electricians (I2). So the corridor needs a stronger response (German pay is the pull); at I2’s rate it brings ~219 applications. The 9 Nov test decides; if it fails, the budget rises (slide 7).
Two-week tests: bars are set from each initiative's planned volume in its own 14-day window (inputs TP1–TK2 on Assumptions)
Initiative | Test window (14 days from launch) | Share of planned volume in window (days of each spend week inside the window) | Test budget € | Planned qualified in window | Planned cost per qualified | PASS if qualified ≥ | …and cost per qualified ≤ | KILL if qualified < | …or cost per qualified > | Other conditions
I1 Rediscovery + referrals | Wed 21 Oct – Tue 3 Nov (waves 1–3) | 89% | 63.3 | 24.5433 | n/a (≈€8) | 14 | – | 8 | – | A kill means no more re-contact waves; the referral bonus stays live (paid only on a signed hire).
I2 Handwerk → Industrie | Fri 23 Oct – Thu 5 Nov (read Mon 9 Nov) | 44.02% | 5563.1143 | 12.9855 | 336 | 7 | 500 | 4 | 670 | Also stop at once if the client rejects the profile; the money moves to programmatic electricians.
I3 Polish corridor | Tue 27 Oct – Mon 9 Nov (freelancer starts 27 Oct) | 42.69% | 3172.0817 | 20.6982 | 133.9286 | 12 | 200 | 7 | 270 | Also stop if far fewer than planned pass the language call. The freelancer is paid hourly, so stopping costs little.
Who does what is on deck slide 7. I2 and I3 are read on Mon 9 Nov, I1 on Mon 2 Nov.

## Channels
Part 2 — Channel × role economics and allocation (cheapest cost-per-hire first, until each role's openings are covered)
How hires are bought: within each role, channels are used cheapest cost per hire first, each up to its volume cap, until openings are filled.
Every paid channel first gets a €750 test in weeks 1–2; its hires count. Then only the remaining need is bought.
ID | Channel | Role | Type | Basis | Unit cost € | Click→apply / apps per slot | Cost per application | Share qualified | Max applications | Qualified capacity | Qualified → signed | Downstream adj. | Hire capacity | Cost per qualified | Cost per hire at capacity (incl. fixed) | Sort key | Rank in role | Remaining capacity of cheaper channels | Need after all tests (openings – test hires) | Hires (test + allocated) | Qualified (total) | Applications (total) | Media € (incl. test tranche) | Fixed € | Test tranche wk 1–2 € | Total € | Planned cost per hire | Rank overall | Status | Test applications | Test qualified | Test hires | Hire capacity left after test | Hires allocated beyond test
C01 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Electricians | Channel | Free | 0 |  | 0 | 17.5% | 105 | 18.375 | 31.5% | 1 | 5.7881 | 0 | 0 | 5e-06 | 1 | 0 | 29.1506 | 5.7881 | 18.375 | 105 | 0 | 0 | 0 | 0 | 0 | 1 | Used to capacity | 0 | 0 | 0 | 5.7881 | 5.7881
C02 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Mechatronics | Channel | Free | 0 |  | 0 | 17.5% | 158 | 27.65 | 37.12% | 1 | 10.2651 | 0 | 0 | 6e-06 | 1 | 0 | 43.9989 | 10.2651 | 27.65 | 158 | 0 | 0 | 0 | 0 | 0 | 2 | Used to capacity | 0 | 0 | 0 | 10.2651 | 10.2651
C03 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Automation | Channel | Free | 0 |  | 0 | 17.5% | 53 | 9.275 | 28.35% | 1 | 2.6295 | 0 | 0 | 7e-06 | 1 | 0 | 13.9966 | 2.6295 | 9.275 | 53 | 0 | 0 | 0 | 0 | 0 | 3 | Used to capacity | 0 | 0 | 0 | 2.6295 | 2.6295
C04 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Supervisors | Channel | Free | 0 |  | 0 | 16.1% | 35 | 5.635 | 23.8% | 1 | 1.3411 | 0 | 0 | 8e-06 | 1 | 0 | 9.2251 | 1.3411 | 5.635 | 35 | 0 | 0 | 0 | 0 | 0 | 4 | Used to capacity | 0 | 0 | 0 | 1.3411 | 1.3411
C05 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Electricians | Channel | CPA | 161 | 0 | 161 | 22.5% | 910 | 204.75 | 31.5% | 1 | 64.4963 | 715.5556 | 2271.6049 | 2271.6049 | 6 | 20.5254 | 29.1506 | 8.9553 | 28.4297 | 126.3541 | 20343.0129 | 0 | 750 | 20343.0129 | 2271.6049 | 22 | Marginal (fills the gap) | 4.6584 | 1.0481 | 0.33016 | 64.1661 | 8.6252
C06 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Mechatronics | Channel | CPA | 161 | 0 | 161 | 22.5% | 4690 | 1055.25 | 37.12% | 1 | 391.7616 | 715.5556 | 1927.4224 | 1927.4224 | 6 | 37.2118 | 43.9989 | 7.1762 | 19.3299 | 85.9105 | 13831.5844 | 0 | 750 | 13831.5844 | 1927.4224 | 19 | Marginal (fills the gap) | 4.6584 | 1.0481 | 0.38912 | 391.3724 | 6.7871
C07 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Automation | Channel | CPA | 161 | 0 | 161 | 22.5% | 380 | 85.5 | 28.35% | 1 | 24.2392 | 715.5556 | 2524.0055 | 2524.0055 | 6 | 16.2252 | 13.9966 | 0.29715 | 1.0481 | 4.6584 | 750 | 0 | 750 | 750 | 2524.0055 | 24 | Test only (wk 1–2) | 4.6584 | 1.0481 | 0.29715 | 23.9421 | 0
C08 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Supervisors | Channel | CPA | 161 | 0 | 161 | 20.7% | 430 | 89.01 | 23.8% | 1 | 21.1844 | 777.7778 | 3267.9739 | 3267.9739 | 6 | 12.0493 | 9.2251 | 0.2295 | 0.96429 | 4.6584 | 750 | 0 | 750 | 750 | 3267.9739 | 28 | Test only (wk 1–2) | 4.6584 | 0.96429 | 0.2295 | 20.9549 | 0
C09 | StepStone (30-day single ad) | Electricians | Channel | Slot | 1449 | 12 | 120.75 | 22.5% | 24 | 5.4 | 31.5% | 1 | 1.701 | 536.6667 | 1703.7037 | 1703.7037 | 5 | 18.8244 | 29.1506 | 1.701 | 5.4 | 24 | 2898 | 0 | 0 | 2898 | 1703.7037 | 17 | Used to capacity | 0 | 0 | 0 | 1.701 | 1.701
C10 | StepStone (30-day single ad) | Mechatronics | Channel | Slot | 1449 | 12 | 120.75 | 22.5% | 24 | 5.4 | 37.12% | 1 | 2.0048 | 536.6667 | 1445.5668 | 1445.5668 | 5 | 35.2071 | 43.9989 | 2.0048 | 5.4 | 24 | 2898 | 0 | 0 | 2898 | 1445.5668 | 15 | Used to capacity | 0 | 0 | 0 | 2.0048 | 2.0048
C11 | StepStone (30-day single ad) | Automation | Channel | Slot | 1449 | 12 | 120.75 | 22.5% | 24 | 5.4 | 28.35% | 1 | 1.5309 | 536.6667 | 1893.0041 | 1893.0041 | 5 | 14.6943 | 13.9966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | – | 18 | Not used | 0 | 0 | 0 | 1.5309 | 0
C12 | StepStone (30-day single ad) | Supervisors | Channel | Slot | 1449 | 12 | 120.75 | 20.7% | 12 | 2.484 | 23.8% | 1 | 0.59119 | 583.3333 | 2450.9804 | 2450.9804 | 5 | 11.4581 | 9.2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | – | 23 | Not used | 0 | 0 | 0 | 0.59119 | 0
C13 | LinkedIn (promoted jobs + InMail) | Automation | Channel | CPA | 96 | 0 | 96 | 22.5% | 160 | 36 | 28.35% | 1 | 10.206 | 426.6667 | 1504.9971 | 1504.9971 | 4 | 4.9866 | 13.9966 | 9.5084 | 33.5392 | 149.063 | 14310.0484 | 0 | 750 | 14310.0484 | 1504.9971 | 16 | Marginal (fills the gap) | 7.8125 | 1.7578 | 0.49834 | 9.7077 | 9.01
C14 | LinkedIn (promoted jobs + InMail) | Supervisors | Channel | CPA | 96 | 0 | 96 | 20.7% | 180 | 37.26 | 23.8% | 1 | 8.8679 | 463.7681 | 1948.6055 | 1948.6055 | 4 | 2.9751 | 9.2251 | 6.6348 | 27.8774 | 134.6736 | 12928.6678 | 0 | 750 | 12928.6678 | 1948.6055 | 20 | Marginal (fills the gap) | 7.8125 | 1.6172 | 0.38489 | 8.483 | 6.2499
C15 | Meta social (FB/IG lead ads, 75 km geo) | Electricians | Channel | CPA | 84 | 0 | 84 | 10.25% | 200 | 20.5 | 31.5% | 1 | 6.4575 | 819.5122 | 2601.626 | 2601.626 | 7 | 84.6915 | 29.1506 | 0.28828 | 0.91518 | 8.9286 | 750 | 0 | 750 | 750 | 2601.626 | 25 | Test only (wk 1–2) | 8.9286 | 0.91518 | 0.28828 | 6.1692 | 0
C16 | Meta social (FB/IG lead ads, 75 km geo) | Mechatronics | Channel | CPA | 84 | 0 | 84 | 10.25% | 220 | 22.55 | 37.12% | 1 | 8.3717 | 819.5122 | 2207.4403 | 2207.4403 | 7 | 428.5843 | 43.9989 | 0.33976 | 0.91518 | 8.9286 | 750 | 0 | 750 | 750 | 2207.4403 | 21 | Test only (wk 1–2) | 8.9286 | 0.91518 | 0.33976 | 8.0319 | 0
C17 | Google Search ads (job-intent keywords) | Electricians | Channel | CPA | 179 | 0 | 179 | 17.5% | 340 | 59.5 | 31.5% | 1 | 18.7425 | 1022.8571 | 3247.1655 | 3247.1656 | 8 | 90.8607 | 29.1506 | 0.23097 | 0.73324 | 4.1899 | 750 | 0 | 750 | 750 | 3247.1655 | 27 | Test only (wk 1–2) | 4.1899 | 0.73324 | 0.23097 | 18.5115 | 0
C18 | Google Search ads (job-intent keywords) | Mechatronics | Channel | CPA | 179 | 0 | 179 | 17.5% | 1760 | 308 | 37.12% | 1 | 114.345 | 1022.8571 | 2755.1708 | 2755.1708 | 8 | 436.6162 | 43.9989 | 0.27222 | 0.73324 | 4.1899 | 750 | 0 | 750 | 750 | 2755.1708 | 26 | Test only (wk 1–2) | 4.1899 | 0.73324 | 0.27222 | 114.0728 | 0
C19 | Google Search ads (job-intent keywords) | Automation | Channel | CPA | 179 | 0 | 179 | 17.5% | 140 | 24.5 | 28.35% | 1 | 6.9458 | 1022.8571 | 3607.9617 | 3607.9617 | 7 | 40.1673 | 13.9966 | 0.20787 | 0.73324 | 4.1899 | 750 | 0 | 750 | 750 | 3607.9617 | 29 | Test only (wk 1–2) | 4.1899 | 0.73324 | 0.20787 | 6.7379 | 0
C20 | Google Search ads (job-intent keywords) | Supervisors | Channel | CPA | 179 | 0 | 179 | 16.1% | 160 | 25.76 | 23.8% | 1 | 6.1309 | 1111.8012 | 4671.4338 | 4671.4338 | 7 | 33.0042 | 9.2251 | 0.16055 | 0.67458 | 4.1899 | 750 | 0 | 750 | 750 | 4671.4338 | 30 | Test only (wk 1–2) | 4.1899 | 0.67458 | 0.16055 | 5.9703 | 0
I1a-E | I1a Talent rediscovery (past applicants in ATS) | Electricians | Initiative | CPA | 2.5 |  | 2.5 | 50% | 7.8 | 3.9 | 36.23% | 1.15 | 1.4128 | 5 | 13.8026 | 13.8026 | 2 | 5.7881 | 29.1506 | 1.4128 | 3.9 | 7.8 | 19.5 | 0 | 0 | 19.5 | 13.8026 | 6 | Used to capacity | 0 | 0 | 0 | 1.4128 | 1.4128
I1a-M | I1a Talent rediscovery (past applicants in ATS) | Mechatronics | Initiative | CPA | 2.5 |  | 2.5 | 50% | 9.12 | 4.56 | 42.69% | 1.15 | 1.9468 | 5 | 11.7113 | 11.7113 | 2 | 10.2651 | 43.9989 | 1.9468 | 4.56 | 9.12 | 22.8 | 0 | 0 | 22.8 | 11.7113 | 5 | Used to capacity | 0 | 0 | 0 | 1.9468 | 1.9468
I1a-A | I1a Talent rediscovery (past applicants in ATS) | Automation | Initiative | CPA | 2.5 |  | 2.5 | 50% | 4.56 | 2.28 | 32.6% | 1.15 | 0.74334 | 5 | 15.3362 | 15.3363 | 2 | 2.6295 | 13.9966 | 0.74334 | 2.28 | 4.56 | 11.4 | 0 | 0 | 11.4 | 15.3362 | 7 | Used to capacity | 0 | 0 | 0 | 0.74334 | 0.74334
I1a-S | I1a Talent rediscovery (past applicants in ATS) | Supervisors | Initiative | CPA | 2.5 |  | 2.5 | 50% | 3.84 | 1.92 | 27.37% | 1.15 | 0.5255 | 5 | 18.2682 | 18.2682 | 2 | 1.3411 | 9.2251 | 0.5255 | 1.92 | 3.84 | 9.6 | 0 | 0 | 9.6 | 18.2682 | 8 | Used to capacity | 0 | 0 | 0 | 0.5255 | 0.5255
I1b-E | I1b Employee referral sprint (bonus on hire) | Electricians | Initiative | CPA | 163.0125 |  | 163.0125 | 45% | 20 | 9 | 36.23% | 1.15 | 3.2603 | 362.25 | 1000 | 1000 | 3 | 7.2009 | 29.1506 | 3.2603 | 9 | 20 | 3260.25 | 0 | 0 | 3260.25 | 1000 | 10 | Used to capacity | 0 | 0 | 0 | 3.2603 | 3.2603
I1b-M | I1b Employee referral sprint (bonus on hire) | Mechatronics | Initiative | CPA | 192.1219 |  | 192.1219 | 45% | 26 | 11.7 | 42.69% | 1.15 | 4.9952 | 426.9375 | 1000 | 1000 | 4 | 30.2119 | 43.9989 | 4.9952 | 11.7 | 26 | 4995.1687 | 0 | 0 | 4995.1687 | 1000 | 11 | Used to capacity | 0 | 0 | 0 | 4.9952 | 4.9952
I1b-A | I1b Employee referral sprint (bonus on hire) | Automation | Initiative | CPA | 146.7113 |  | 146.7113 | 45% | 11 | 4.95 | 32.6% | 1.15 | 1.6138 | 326.025 | 1000 | 1000 | 3 | 3.3728 | 13.9966 | 1.6138 | 4.95 | 11 | 1613.8238 | 0 | 0 | 1613.8238 | 1000 | 12 | Used to capacity | 0 | 0 | 0 | 1.6138 | 1.6138
I1b-S | I1b Employee referral sprint (bonus on hire) | Supervisors | Initiative | CPA | 123.165 |  | 123.165 | 45% | 9 | 4.05 | 27.37% | 1.15 | 1.1085 | 273.7 | 1000 | 1000 | 3 | 1.8666 | 9.2251 | 1.1085 | 4.05 | 9 | 1108.485 | 0 | 0 | 1108.485 | 1000 | 13 | Used to capacity | 0 | 0 | 0 | 1.1085 | 1.1085
I2-E | I2 Handwerk → Industrie (construction electricians) | Electricians | Initiative | CPA | 84 |  | 84 | 25% | 118 | 29.5 | 28.35% | 0.9 | 8.3633 | 336 | 1328.6701 | 1328.6701 | 4 | 10.4611 | 29.1506 | 8.3633 | 29.5 | 118 | 9912 | 1200 | 0 | 11112 | 1328.6701 | 14 | Used to capacity | 0 | 0 | 0 | 8.3633 | 8.3633
I3-M | I3 Polish border corridor + PL pre-screener | Mechatronics | Initiative | CPA | 18.75 |  | 18.75 | 14% | 350 | 49 | 37.12% | 1 | 18 | 133.9286 | 382.9726 | 382.9726 | 3 | 12.2119 | 43.9989 | 18 | 48.4848 | 346.3203 | 6493.5065 | 400 | 0 | 6893.5065 | 382.9726 | 9 | Used to capacity | 0 | 0 | 0 | 18 | 18
Total | [8 empty] | 10564.32 | 2169.059 |  |  | 749.5697 | [6 empty] | 100 | 307.9731 | 1494.5752 | 100655.8476 | 1600 | 9000 | 102255.8476 | 1022.5585 |  |  | 68.8755 | 12.1884 | 3.6288 |  | 96.3712
Role coverage check
| Role | Openings | Hires planned (test + allocated) | Shortfall
| Electricians | 30 | 30 | 0
| Mechatronics | 45 | 45 | 0
| Automation | 15 | 15 | 0
| Supervisors | 10 | 10 | 0

## Budget
Part 2.4 — Recommended budget and allocation
How: planned spend = paid media + initiatives + set-up (from Channels); reserve = 15% of the total; rounded up to the next €2,500.
| Paid channels: media (incl. test tranches) | 73209.3136
| New initiatives: media + referral bonuses | 27446.534
| New initiatives: fixed set-up costs (Polish translation, German creative + quiz tool) | 1600
| Media + initiatives to hit plan | 102255.8476
| …of which test tranches in weeks 1–2 (info) | 9000
| Planned spend (allocated to channels × weeks) | 102255.8476
| Reserve (unallocated; released from wk 3 by Tracker rules) | 18045.1496
| Total budget (calculated) | 120300.9971
| RECOMMENDED BUDGET (rounded up, step B5) | 122500
| Expected signed hires (capped by assessment slots, Funnel B26) | 100
| Media cost per hire (planned spend ÷ hires) | 1022.5585
| All-in cost per hire if reserve is spent | 1225
| Share of recommended budget spent in weeks 1–2 | 39.75%
By role
| Role | Media € | Fixed € | …of which tests € | Total € | Hires | Cost per hire | Qualified applicants
| Electricians | 37932.7629 | 1200 | 2250 | 39132.7629 | 30 | 1304.4254 | 96.2531
| Mechatronics | 29741.0596 | 400 | 2250 | 30141.0596 | 45 | 669.8013 | 118.7731
| Automation | 17435.2722 | 0 | 2250 | 17435.2722 | 15 | 1162.3515 | 51.8256
| Supervisors | 15546.7528 | 0 | 2250 | 15546.7528 | 10 | 1554.6753 | 41.1213
| Total | 100655.8476 | 1600 | 9000 | 102255.8476 | 100 | 1022.5585 | 307.9731
By channel
| Channel | Total € | Hires | Cost per hire | Share of planned spend
| Organic (Tesla careers, BA Jobbörse, Google for Jobs) | 0 | 20.0238 | 0 | 0%
| Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | 35674.5973 | 16.6582 | 2141.5634 | 34.89%
| StepStone (30-day single ad) | 5796 | 3.7058 | 1564.0559 | 5.668%
| LinkedIn (promoted jobs + InMail) | 27238.7163 | 16.1432 | 1687.3196 | 26.64%
| Meta social (FB/IG lead ads, 75 km geo) | 1500 | 0.62804 | 2388.378 | 1.467%
| Google Search ads (job-intent keywords) | 3000 | 0.87161 | 3441.9064 | 2.934%
| I1a Talent rediscovery (past applicants in ATS) | 63.3 | 4.6285 | 13.6763 | 0.0619%
| I1b Employee referral sprint (bonus on hire) | 10977.7275 | 10.9777 | 1000 | 10.74%
| I2 Handwerk → Industrie (construction electricians) | 11112 | 8.3633 | 1328.6701 | 10.87%
| I3 Polish border corridor + PL pre-screener | 6893.5065 | 18 | 382.9726 | 6.741%
| Total | 102255.8476 | 100
✓ ties to planned spend
Part 2.5 — What 30% less budget buys
If money is cut: drop the most expensive cost-per-hire cells first and keep the reserve at 15%. If assessment slots run out, hires are capped (scenario detail below).
| Budget level | Total budget € | Electricians | Mechatronics | Automation | Supervisors | Total hires | Cost per hire
| 100% | 122500 | 30 | 45 | 15 | 10 | 100 | 1225
| 70% | 85750 | 20.5254 | 43.98 | 14.495 | 8.0574 | 87.0578 | 984.9777
Budget scenarios: cut the most expensive cost-per-hire cells first
Cells are cut in order of planned cost per hire (most expensive first). A cut removes media first; a cell's set-up cost is only saved once its media is fully cut, so partially cut cells keep their set-up.
|  |  |  | Budget level → | 100% | 70%
|  |  |  | Total budget € | 122500 | 85750
|  |  |  | Spend available (after reserve) € | 104125 | 72887.5
|  |  |  | Savings needed € | 0 | 29368.3476
ID (+ to expand) | Role | Total € (media + fixed) | Sort key (planned cost per hire) | Hires | Hires @ recommended | Hires @ cut |  |  | Cut € @ recommended | Cut € @ cut | Media € | Qualified @ recommended | Qualified @ cut
C01 | Electricians | 0 | 5.6e-05 | 5.7881 | 5.7881 | 5.7881 |  |  | 0 | 0 | 0 | 18.375 | 18.375
C02 | Mechatronics | 0 | 5.7e-05 | 10.2651 | 10.2651 | 10.2651 |  |  | 0 | 0 | 0 | 27.65 | 27.65
C03 | Automation | 0 | 5.8e-05 | 2.6295 | 2.6295 | 2.6295 |  |  | 0 | 0 | 0 | 9.275 | 9.275
C04 | Supervisors | 0 | 5.9e-05 | 1.3411 | 1.3411 | 1.3411 |  |  | 0 | 0 | 0 | 5.635 | 5.635
C05 | Electricians | 20343.0129 | 2271.605 | 8.9553 | 8.9553 | 0 |  |  | 0 | 20343.0129 | 20343.0129 | 28.4297 | 0
C06 | Mechatronics | 13831.5844 | 1927.4224 | 7.1762 | 7.1762 | 7.1762 |  |  | 0 | 0 | 13831.5844 | 19.3299 | 19.3299
C07 | Automation | 750 | 2524.0055 | 0.29715 | 0.29715 | 0 |  |  | 0 | 750 | 750 | 1.0481 | 0
C08 | Supervisors | 750 | 3267.9739 | 0.2295 | 0.2295 | 0 |  |  | 0 | 750 | 750 | 0.96429 | 0
C09 | Electricians | 2898 | 1703.7038 | 1.701 | 1.701 | 1.701 |  |  | 0 | 0 | 2898 | 5.4 | 5.4
C10 | Mechatronics | 2898 | 1445.5668 | 2.0048 | 2.0048 | 2.0048 |  |  | 0 | 0 | 2898 | 5.4 | 5.4
C11 | Automation | 0 | 6.6e-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
C12 | Supervisors | 0 | 6.7e-05 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
C13 | Automation | 14310.0484 | 1504.9971 | 9.5084 | 9.5084 | 9.5084 |  |  | 0 | 0 | 14310.0484 | 33.5392 | 33.5392
C14 | Supervisors | 12928.6678 | 1948.6056 | 6.6348 | 6.6348 | 5.0823 |  |  | 0 | 3025.3346 | 12928.6678 | 27.8774 | 21.3541
C15 | Electricians | 750 | 2601.6261 | 0.28828 | 0.28828 | 0 |  |  | 0 | 750 | 750 | 0.91518 | 0
C16 | Mechatronics | 750 | 2207.4403 | 0.33976 | 0.33976 | 0 |  |  | 0 | 750 | 750 | 0.91518 | 0
C17 | Electricians | 750 | 3247.1656 | 0.23097 | 0.23097 | 0 |  |  | 0 | 750 | 750 | 0.73324 | 0
C18 | Mechatronics | 750 | 2755.1708 | 0.27222 | 0.27222 | 0 |  |  | 0 | 750 | 750 | 0.73324 | 0
C19 | Automation | 750 | 3607.9618 | 0.20787 | 0.20787 | 0 |  |  | 0 | 750 | 750 | 0.73324 | 0
C20 | Supervisors | 750 | 4671.4339 | 0.16055 | 0.16055 | 0 |  |  | 0 | 750 | 750 | 0.67458 | 0
I1a-E | Electricians | 19.5 | 13.8027 | 1.4128 | 1.4128 | 1.4128 |  |  | 0 | 0 | 19.5 | 3.9 | 3.9
I1a-M | Mechatronics | 22.8 | 11.7114 | 1.9468 | 1.9468 | 1.9468 |  |  | 0 | 0 | 22.8 | 4.56 | 4.56
I1a-A | Automation | 11.4 | 15.3363 | 0.74334 | 0.74334 | 0.74334 |  |  | 0 | 0 | 11.4 | 2.28 | 2.28
I1a-S | Supervisors | 9.6 | 18.2683 | 0.5255 | 0.5255 | 0.5255 |  |  | 0 | 0 | 9.6 | 1.92 | 1.92
I1b-E | Electricians | 3260.25 | 1000.0001 | 3.2603 | 3.2603 | 3.2603 |  |  | 0 | 0 | 3260.25 | 9 | 9
I1b-M | Mechatronics | 4995.1687 | 1000.0001 | 4.9952 | 4.9952 | 4.9952 |  |  | 0 | 0 | 4995.1687 | 11.7 | 11.7
I1b-A | Automation | 1613.8238 | 1000.0001 | 1.6138 | 1.6138 | 1.6138 |  |  | 0 | 0 | 1613.8238 | 4.95 | 4.95
I1b-S | Supervisors | 1108.485 | 1000.0001 | 1.1085 | 1.1085 | 1.1085 |  |  | 0 | 0 | 1108.485 | 4.05 | 4.05
I2-E | Electricians | 11112 | 1328.6702 | 8.3633 | 8.3633 | 8.3633 |  |  | 0 | 0 | 9912 | 29.5 | 29.5
I3-M | Mechatronics | 6893.5065 | 382.9727 | 18 | 18 | 17.592 |  |  | 0 | 0 | 6493.5065 | 48.4848 | 47.3859
Hires by role
|  |  |  | Electricians | 30 | 20.5254
|  |  |  | Mechatronics | 45 | 43.98
|  |  |  | Automation | 15 | 14.495
|  |  |  | Supervisors | 10 | 8.0574
|  |  |  | Total | 100 | 87.0578
|  |  |  | Cost per hire | 1225 | 984.9777
|  |  |  | Qualified applicants (before capacity cap) | 307.9731 | 265.204
|  |  |  | Capacity factor (assessment slots ÷ qualified, max 1) | 100% | 100%
Hires by role are scaled by the capacity factor: if a scenario's qualified applicants exceed the assessment slots, only the share that can be assessed turns into hires (same rule as Budget C13).

## Weekly
Week-by-week plan: cash out, qualified flow vs 55/week, signatures
Cash by week: tests in weeks 1–2, StepStone ads and set-up in week 1, media by the weekly shares, referral bonuses when people sign (signatures land ~24 days after application, rounded to whole weeks).
Week | Start (Tue) | End | Spend share E/M/A | Spend share Supervisors | Signing share E/M/A | Signing share Supervisors | CPC/CPA media after tests € | StepStone ads € | Referral bonuses € | Set-up costs € | Test tranches € | Cash out € | Cumulative € | Applications | Qualified arriving | Assessment slots | Slot use | Flag | Signed (E/M/A) | Signed (Supervisors) | Signed total | Cum. signed | Test share | Rediscovery share | Input share (Assumptions W1–W11) | Supervisor share before re-scaling (useful days only) | I2 share (from go-live) | I3 share (from go-live) | I2 share before re-scaling | I3 share before re-scaling | I2 live days (fallback) | I3 live days (fallback)
1 | 2026-10-20 | 2026-10-26 | 31.6% | 39.21% | 0% | 0% | 21493.9239 | 5796 | 0 | 1600 | 3600 | 32489.9239 | 32489.9239 | 376.1895 | 86.1933 | 86.4286 | 99.73% | Full | 0 | 0 | 0 | 0 | 40% | 60% | 31.6% | 31.6% | 20.89% | 0% | 18.06% | 0% | 4 | 0
2 | 2026-10-27 | 2026-11-02 | 13.1% | 16.26% | 0% | 0% | 10800.365 | 0 | 0 | 0 | 5400 | 16200.365 | 48690.2889 | 260.891 | 52.7478 | 55 | 95.91% | Full | 0 | 0 | 0 | 0 | 60% | 29% | 13.1% | 13.1% | 15.15% | 19.15% | 13.1% | 13.1% | 7 | 7
3 | 2026-11-03 | 2026-11-09 | 16.1% | 19.98% | 0% | 0% | 13258.1331 | 0 | 0 | 0 | 0 | 13258.1331 | 61948.422 | 263.6088 | 52.7202 | 55 | 95.85% | Full | 0 | 0 | 0 | 0 | 0% | 11% | 16.1% | 16.1% | 18.62% | 23.54% | 16.1% | 16.1% | 7 | 7
4 | 2026-11-10 | 2026-11-16 | 17% | 21.1% | 31.6% | 0% | 13991.9187 | 0 | 3118.6806 | 0 | 0 | 17110.5994 | 79059.0214 | 275.4038 | 54.1968 | 55 | 98.54% | Full | 23.2609 | 0 | 23.2609 | 23.2609 | 0% | 0% | 17% | 17% | 19.66% | 24.85% | 17% | 17% | 7 | 7
5 | 2026-11-17 | 2026-11-23 | 19.5% | 3.457% | 13.1% | 39.21% | 13523.576 | 0 | 1727.5399 | 0 | 0 | 15251.1159 | 94310.1373 | 280.4661 | 54.7115 | 55 | 99.48% | Full | 15.0418 | 4.0366 | 19.0784 | 42.3393 | 0% | 0% | 19.5% | 2.786% | 22.55% | 28.51% | 19.5% | 19.5% | 7 | 7
6 | 2026-11-24 | 2026-11-30 | 2.7% | 0% | 16.1% | 16.26% | 1814.2033 | 0 | 1769.1432 | 0 | 0 | 3583.3465 | 97893.4838 | 38.016 | 7.4034 | 7.8571 | 94.23% | Full | 15.371 | 2.0316 | 17.4026 | 59.7419 | 0% | 0% | 2.7% | 0% | 3.123% | 3.947% | 2.7% | 2.7% | 1 | 1
7 | 2026-12-01 | 2026-12-07 | 0% | 0% | 17% | 19.98% | 0 | 0 | 1899.2324 | 0 | 0 | 1899.2324 | 99792.7162 | 0 | 0 | 0 | 0% |  | 15.7537 | 1.7959 | 17.5496 | 77.2915 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
8 | 2026-12-08 | 2026-12-14 | 0% | 0% | 19.5% | 21.1% | 0 | 0 | 2158.3433 | 0 | 0 | 2158.3433 | 101951.0595 | 0 | 0 | 0 | 0% |  | 18.0705 | 1.8352 | 19.9057 | 97.1972 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
9 | 2026-12-15 | 2026-12-21 | 0% | 0% | 2.7% | 3.457% | 0 | 0 | 304.788 | 0 | 0 | 304.788 | 102255.8476 | 0 | 0 | 0 | 0% |  | 2.5021 | 0.30073 | 2.8028 | 100 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
10 | 2026-12-22 | 2026-12-28 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 102255.8476 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 100 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
11 | 2026-12-29 | 2026-12-31 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 102255.8476 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 100 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
Total |  |  | 100% | 100% | 100% | 100% | 74882.1201 | 5796 | 10977.7275 | 1600 | 9000 | 102255.8476 |  | 1494.5752 | 307.9731 | 314.2857 |  | ✓ ties to plan | 90 | 10 | 100 |  | 100% | 1 | 1
Weak channels are cut from Mon 2 Nov; tests are judged by Mon 9 Nov; the reserve is released only from week 3, on the Tracker rules.
Helper totals | [6 empty] | Late launches (paced from their go-live dates, cols AB–AE)
| Spreadable media E/M/A (after tests, excl. rediscovery) |  |  |  | 62640.1522 |  | I2 media € |  |  |  | 9912
| Spreadable media Supervisors (after tests, excl. rediscovery) |  |  |  | 12178.6678 |  | I2 applications |  |  |  | 118
| StepStone ads (all roles) |  |  |  | 5796 |  | I2 qualified |  |  |  | 29.5
| Referral bonuses E/M/A |  |  |  | 9869.2425 |  | I2 hires |  |  |  | 8.3633
| Referral bonuses Supervisors |  |  |  | 1108.485 |  | I3 media € |  |  |  | 6493.5065
| Test tranches (all roles) |  |  |  | 9000 |  | I3 applications |  |  |  | 346.3203
| Test qualified E/M/A |  |  |  | 8.9323 |  | I3 qualified |  |  |  | 48.4848
| Test qualified Supervisors |  |  |  | 3.2561 |  | I3 hires |  |  |  | 18
| Test applications E/M/A |  |  |  | 52.2146
| Test applications Supervisors |  |  |  | 16.6608
| Test hires E/M/A |  |  |  | 2.8539
| Test hires Supervisors |  |  |  | 0.77494
| Rediscovery spend (all roles) |  |  |  | 63.3
| Rediscovery qualified E/M/A |  |  |  | 10.74
| Rediscovery qualified Supervisors |  |  |  | 1.92
| Rediscovery applications E/M/A |  |  |  | 21.48
| Rediscovery applications Supervisors |  |  |  | 3.84
| Rediscovery hires E/M/A |  |  |  | 4.1029
| Rediscovery hires Supervisors |  |  |  | 0.5255
| Capacity factor (share of planned qualified that can be assessed) |  |  |  | 100%
Cash out by channel × week (€)
| Channel | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Total
| Organic (Tesla careers, BA Jobbörse, Google for Jobs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | 11525.1727 | 6080.3722 | 5260.6102 | 5554.6815 | 6371.5465 | 882.2141 | 0 | 0 | 0 | 0 | 0 | 35674.5973
| StepStone (30-day single ad) | 5796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5796
| LinkedIn (promoted jobs + InMail) | 9660.5848 | 4656.1285 | 4616.3106 | 4874.3652 | 3065.2058 | 366.1213 | 0 | 0 | 0 | 0 | 0 | 27238.7163
| Meta social (FB/IG lead ads, 75 km geo) | 600 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
| Google Search ads (job-intent keywords) | 1200 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
| I1a Talent rediscovery (past applicants in ATS) | 37.98 | 18.357 | 6.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.3
| I1b Employee referral sprint (bonus on hire) | 0 | 0 | 0 | 3118.6806 | 1727.5399 | 1769.1432 | 1899.2324 | 2158.3433 | 304.788 | 0 | 0 | 10977.7275
| I2 Handwerk → Industrie (construction electricians) | 3270.1864 | 1501.8678 | 1845.807 | 1948.9888 | 2235.6048 | 309.5453 | 0 | 0 | 0 | 0 | 0 | 11112
| I3 Polish border corridor + PL pre-screener | 400 | 1243.6394 | 1528.4423 | 1613.8832 | 1851.219 | 256.3226 | 0 | 0 | 0 | 0 | 0 | 6893.5065
| Total | 32489.9239 | 16200.365 | 13258.1331 | 17110.5994 | 15251.1159 | 3583.3465 | 1899.2324 | 2158.3433 | 304.788 | 0 | 0 | 102255.8476
✓ matrix ties to planned spend
Formulas:
Start (Tue) = Assumptions!$D7+7*([Week]-1)
End = MIN([Start (Tue)]+6,Assumptions!$D8)

## Tracker
Weekly tracker — type actuals in the yellow cells; decisions and re-forecast update live
Source: client ATS export by source tag (utm_source/utm_campaign → ATS 'source' field) + Joveo platform spend/clicks/applies. Updated every Monday for the prior week.
ID | Channel | Role | Plan CPA | Plan Q | Plan cost per qual. | W1 spend | W1 apps | W1 qual. | W2 spend | W2 apps | W2 qual. | W3 spend | W3 apps | W3 qual. | Cum. spend | Cum. apps | Cum. qual. | Actual CPA | Actual Q | Q used | Re-forecast cost per qual. | vs plan | Decision | Signed to date (ATS source tag) | Cost per hire to date | Plan hires
C01 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Electricians | 0 | 17.5% | 0 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 0 |  | Free – monitor quality |  |  | 5.7881
C02 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Mechatronics | 0 | 17.5% | 0 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 0 |  | Free – monitor quality |  |  | 10.2651
C03 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Automation | 0 | 17.5% | 0 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 0 |  | Free – monitor quality |  |  | 2.6295
C04 | Organic (Tesla careers, BA Jobbörse, Google for Jobs) | Supervisors | 0 | 16.1% | 0 | [9 empty] | 0 | 0 | 0 |  |  | 16.1% | 0 |  | Free – monitor quality |  |  | 1.3411
C05 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Electricians | 161 | 22.5% | 715.5556 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 715.5556 | 1 | Wait – too little data |  |  | 8.9553
C06 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Mechatronics | 161 | 22.5% | 715.5556 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 715.5556 | 1 | Wait – too little data |  |  | 7.1762
C07 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Automation | 161 | 22.5% | 715.5556 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 715.5556 | 1 | Wait – too little data |  |  | 0.29715
C08 | Programmatic job ads (Joveo: Indeed, Jooble, Talent.com, Kimeta, meinestadt…) | Supervisors | 161 | 20.7% | 777.7778 | [9 empty] | 0 | 0 | 0 |  |  | 20.7% | 777.7778 | 1 | Wait – too little data |  |  | 0.2295
C09 | StepStone (30-day single ad) | Electricians | 120.75 | 22.5% | 536.6667 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 536.6667 | 1 | Wait – too little data |  |  | 1.701
C10 | StepStone (30-day single ad) | Mechatronics | 120.75 | 22.5% | 536.6667 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 536.6667 | 1 | Wait – too little data |  |  | 2.0048
C11 | StepStone (30-day single ad) | Automation | 120.75 | 22.5% | 536.6667 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 536.6667 | 1 | Wait – too little data |  |  | 0
C12 | StepStone (30-day single ad) | Supervisors | 120.75 | 20.7% | 583.3333 | [9 empty] | 0 | 0 | 0 |  |  | 20.7% | 583.3333 | 1 | Wait – too little data |  |  | 0
C13 | LinkedIn (promoted jobs + InMail) | Automation | 96 | 22.5% | 426.6667 | [9 empty] | 0 | 0 | 0 |  |  | 22.5% | 426.6667 | 1 | Wait – too little data |  |  | 9.5084
C14 | LinkedIn (promoted jobs + InMail) | Supervisors | 96 | 20.7% | 463.7681 | [9 empty] | 0 | 0 | 0 |  |  | 20.7% | 463.7681 | 1 | Wait – too little data |  |  | 6.6348
C15 | Meta social (FB/IG lead ads, 75 km geo) | Electricians | 84 | 10.25% | 819.5122 | [9 empty] | 0 | 0 | 0 |  |  | 10.25% | 819.5122 | 1 | Wait – too little data |  |  | 0.28828
C16 | Meta social (FB/IG lead ads, 75 km geo) | Mechatronics | 84 | 10.25% | 819.5122 | [9 empty] | 0 | 0 | 0 |  |  | 10.25% | 819.5122 | 1 | Wait – too little data |  |  | 0.33976
C17 | Google Search ads (job-intent keywords) | Electricians | 179 | 17.5% | 1022.8571 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 1022.8571 | 1 | Wait – too little data |  |  | 0.23097
C18 | Google Search ads (job-intent keywords) | Mechatronics | 179 | 17.5% | 1022.8571 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 1022.8571 | 1 | Wait – too little data |  |  | 0.27222
C19 | Google Search ads (job-intent keywords) | Automation | 179 | 17.5% | 1022.8571 | [9 empty] | 0 | 0 | 0 |  |  | 17.5% | 1022.8571 | 1 | Wait – too little data |  |  | 0.20787
C20 | Google Search ads (job-intent keywords) | Supervisors | 179 | 16.1% | 1111.8012 | [9 empty] | 0 | 0 | 0 |  |  | 16.1% | 1111.8012 | 1 | Wait – too little data |  |  | 0.16055
I1a-E | I1a Talent rediscovery (past applicants in ATS) | Electricians | 2.5 | 50% | 5 | [9 empty] | 0 | 0 | 0 |  |  | 50% | 5 | 1 | Wait – too little data |  |  | 1.4128
I1a-M | I1a Talent rediscovery (past applicants in ATS) | Mechatronics | 2.5 | 50% | 5 | [9 empty] | 0 | 0 | 0 |  |  | 50% | 5 | 1 | Wait – too little data |  |  | 1.9468
I1a-A | I1a Talent rediscovery (past applicants in ATS) | Automation | 2.5 | 50% | 5 | [9 empty] | 0 | 0 | 0 |  |  | 50% | 5 | 1 | Wait – too little data |  |  | 0.74334
I1a-S | I1a Talent rediscovery (past applicants in ATS) | Supervisors | 2.5 | 50% | 5 | [9 empty] | 0 | 0 | 0 |  |  | 50% | 5 | 1 | Wait – too little data |  |  | 0.5255
I1b-E | I1b Employee referral sprint (bonus on hire) | Electricians | 163.0125 | 45% | 362.25 | [9 empty] | 0 | 0 | 0 |  |  | 45% | 362.25 | 1 | Wait – too little data |  |  | 3.2603
I1b-M | I1b Employee referral sprint (bonus on hire) | Mechatronics | 192.1219 | 45% | 426.9375 | [9 empty] | 0 | 0 | 0 |  |  | 45% | 426.9375 | 1 | Wait – too little data |  |  | 4.9952
I1b-A | I1b Employee referral sprint (bonus on hire) | Automation | 146.7113 | 45% | 326.025 | [9 empty] | 0 | 0 | 0 |  |  | 45% | 326.025 | 1 | Wait – too little data |  |  | 1.6138
I1b-S | I1b Employee referral sprint (bonus on hire) | Supervisors | 123.165 | 45% | 273.7 | [9 empty] | 0 | 0 | 0 |  |  | 45% | 273.7 | 1 | Wait – too little data |  |  | 1.1085
I2-E | I2 Handwerk → Industrie (construction electricians) | Electricians | 84 | 25% | 336 | [9 empty] | 0 | 0 | 0 |  |  | 25% | 336 | 1 | Wait – too little data |  |  | 8.3633
I3-M | I3 Polish border corridor + PL pre-screener | Mechatronics | 18.75 | 14% | 133.9286 | [9 empty] | 0 | 0 | 0 |  |  | 14% | 133.9286 | 1 | Wait – too little data |  |  | 18
| Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 100
Role-level funnel actuals (cumulative) → re-forecast hires
| Role | Qualified assessed | Interviewed (result known) | Passed | Offers | Signed | Plan pass | Actual pass | Plan offer→signed | Actual offer→signed | Updated qual.→signed (plan mix) | Remaining planned qualified | Re-forecast hires | Openings | Gap
| Electricians | [5 empty] | 50% | 50% | 70% | 70% | 31.17% | 96.2531 | 30 | 30 | 0
| Mechatronics | [5 empty] | 55% | 55% | 75% | 75% | 37.89% | 118.7731 | 45 | 45 | 0
| Automation | [5 empty] | 45% | 45% | 70% | 70% | 28.94% | 51.8256 | 15 | 15 | 0
| Supervisors | [5 empty] | 40% | 40% | 70% | 70% | 24.32% | 41.1213 | 10 | 10 | 0
| Total | 0 | 0 | 0 | 0 | 0 | [5 empty] | 307.9731 | 100 | 100 | 0
Each Monday: type last week's actuals above. Where a channel has enough data, copy its actual cost per application and updated qualified share into Assumptions §7 (real pass and acceptance rates into §3). The plan then re-ranks itself.